## Slide 1
AegisAI
Product portfolio and research programme
Team briefing
24 months from kickoff
Documentation baseline: 18 September 2026
Notes: AegisAI
Product portfolio and research programme
Project documentation: implementation-plan/README.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.

## Slide 2
Project direction and current status
Four independently usable products share one platform.
Own products
AegisAI owns the workflows, evidence model, customer experience and operations.
First delivery
Human Firewall reaches its first production release within months 3–6.
Implementation status
The documentation defines planned work. Product releases and customer validation remain ahead.
Planning basis
A lean team of 2–4 contributors runs one primary product stream.
02
Notes: Project direction and current status
Four independently usable products share one platform.
Own products: AegisAI owns the workflows, evidence model, customer experience and operations.
First delivery: Human Firewall reaches its first production release within months 3–6.
Implementation status: The documentation defines planned work. Product releases and customer validation remain ahead.
Planning basis: A lean team of 2–4 contributors runs one primary product stream.
Project documentation: implementation-plan/01-portfolio-strategy.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
DETAILED PROJECT REFERENCE
# Portfolio strategy
[Index](README.md) · Design baseline, 18 September 2026 · Owner: Product Lead
## Customer and promise
Initial customer hypothesis: Portuguese SMEs with 20–200 employees, a small IT team or outsourced IT, and a named owner willing to run a measured pilot. This size range is a planning assumption to test, not a verified market conclusion. Prioritise professional services and technology-enabled SMEs for early discovery; avoid safety-critical production environments in the first releases.
Offer usable security workflows, understandable evidence, Portuguese support, and privacy-conscious operation. Do not advertise an autonomous SOC, guaranteed incident prevention, automatic compliance, or a proven training efficacy improvement before supporting evidence exists.
The initial paid product is Human Firewall. Optional secure connectivity supports deployment; it is no longer a mandatory bundled VPN offer. This supersedes the earlier combined access-and-training proposal.
## Portfolio outcomes
| Product | Buyer and user | Own-product differentiation hypothesis | Principal business measure |
|---|---|---|---|
| Human Firewall | SME owner/IT administrator; employees | Practical Portuguese scenarios, transparent adaptation, respectful feedback and simple administration | Paid renewal, usable learning outcomes, administration time |
| Security Operations | IT owner or service partner; investigator | One evidence chain from asset/software exposure to finding and reviewed remediation | Useful findings per investigation hour and renewal |
| Defense Box and Validation | IT provider or local infrastructure owner | Locally processed monitoring plus scoped, repeatable validation and remediation retests | Supportable deployments and verified remediation |
| Agent Security | Engineering/security lead; agent operators | Application-level tool authority and execution evidence connected to identity and model policy | Prevented policy violations with acceptable task success/cost |
Each product can be purchased, enabled, and removed independently. Shared identity, audit and deployment are platform capabilities, not compulsory cross-selling of other modules.
## Scope and operating principles
- One primary product stream; research prototypes cannot quietly become additional supported products.
- EU-managed isolated customer stacks first; edge processing for sensitive telemetry. On-premise commercial support follows repeatable packaging and demonstrated demand.
- Build product-specific intelligence, workflows, UX, integrations and evidence. Reuse cryptography, identity standards, scanners, sensors and execution runtimes where appropriate.
- Use validated rules as initial baselines. Promote ML or agentic behaviour only when it improves a measured outcome at acceptable cost and risk.
- Learning profiles are not employee risk rankings. No biometric emotion inference or personality-based access decisions in client products.
- Guided response precedes approved automation. Models propose; deterministic policy and authorised people control consequential actions.
- Open-source deliverables must be useful and reproducible. Paid offerings fund operation, enterprise administration, integrations and support.
## Wider vision preserved
The longer-term portfolio retains UEBA/graph research, local AI, explainability, controlled adversarial testing, federation, industrial/IoT monitoring, recovery exercises, insurer evidence export, and national-framework mappings. Industrial pilots and international expansion require partner readiness and capacity after the core releases. They are not commitments to launch additional products inside the same lean-team budget.
## Capacity and authority
Roles: Product Lead (PL), Platform/Security Lead (PS), Application Engineer (AE), Research Lead (RL). People may hold multiple roles; production-impacting changes still require a second reviewer. Independent assessment is contracted for each materially new product surface before general availability.
Planning baseline: three full-time equivalents, approximately 60% primary product, 20% research/discovery, 20% maintenance/support. This is 1.8 product FTE, not three full parallel teams. At two contributors, reduce scope or extend dependent milestones; at four, add reliability/customer integration capacity before parallel product launches. If support exceeds 20% for two consecutive sprints, pause feature expansion and remediate the operating burden.
The Product Lead owns scope and pricing; PS owns technical release approval; RL owns research claims. Legal applicability and upstream commercial terms require qualified external confirmation before the relevant commitment. These checks do not block unrelated engineering.
## Decision criteria
At every release gate assess customer use, repeatable delivery, security evidence, operating cost and research honesty. Recruitment, conversion, and effectiveness targets are hypotheses. Failed commercial validation triggers packaging/scope revision; failed safety or isolation tests block release. [Roadmap](08-roadmap-backlog.md) defines sequencing and [production handbook](12-production-handbook.md) defines evidence.

## Slide 3
Team discussion
01 Products
Customer outcomes and release boundaries
02 Platform
Architecture, NetBird and interfaces
03 Research
Experiments, agent workspace and evidence
04 Delivery
Roadmap, owners, business model and release gates
03
Notes: Team discussion
01 Products: Customer outcomes and release boundaries
02 Platform: Architecture, NetBird and interfaces
03 Research: Experiments, agent workspace and evidence
04 Delivery: Roadmap, owners, business model and release gates
Project documentation: implementation-plan/README.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.

## Slide 4
The original vision remains broader than training
Security lifecycle | Portfolio capabilities
Govern and identify | Evidence mapping, assets, software dependencies and data governance
Protect and detect | Learning, access recommendations, local monitoring and UEBA research
Respond and recover | Guided remediation, approved actions and recovery exercises
Longer-term development | Federation, industrial monitoring, insurance evidence and new markets
04
Notes: The original vision remains broader than training
Govern and identify / Evidence mapping, assets, software dependencies and data governance
Protect and detect / Learning, access recommendations, local monitoring and UEBA research
Respond and recover / Guided remediation, approved actions and recovery exercises
Longer-term development / Federation, industrial monitoring, insurance evidence and new markets
Project documentation: implementation-plan/02-source-traceability.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.

## Slide 5
Decisions that reshape the earlier plans
Shorter first product
Gamification has a 3–6-month delivery window, followed by capped maintenance.
Earlier engineering foundations
Identity, deployment, observability and recovery start before the first pilot.
Evidence before claims
Synthetic demonstrations and research prototypes stay distinct from customer results.
Selective upstream reuse
NetBird informs architecture and business design. Its use stays optional.
05
Notes: Decisions that reshape the earlier plans
Shorter first product: Gamification has a 3–6-month delivery window, followed by capped maintenance.
Earlier engineering foundations: Identity, deployment, observability and recovery start before the first pilot.
Evidence before claims: Synthetic demonstrations and research prototypes stay distinct from customer results.
Selective upstream reuse: NetBird informs architecture and business design. Its use stays optional.
Project documentation: implementation-plan/14-decisions.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
DETAILED PROJECT REFERENCE
# Architecture and product decision register
[Index](README.md) · Baseline established 18 September 2026
“Accepted” means the planning direction is selected; it does not mean implemented or legally validated. Product names are working labels. Actual staffing, customer contracts and infrastructure purchases are not established by this pack.
| ADR | Decision / status | Rationale | Revisit trigger / owner |
|---|---|---|---|
| ADR-01 | Accepted: own four-product portfolio, one primary stream | Preserve breadth with lean-team execution | Capacity/customer evidence; PL |
| ADR-02 | Accepted: training delivered in M3–6 | First commercial learning cycle; prevent indefinite gamification focus | Gate failure changes breadth, not silent quality reduction; PL |
| ADR-03 | Accepted: Operations → Defense Box → Agent Security | User-selected priority order | Explicit portfolio review/user direction; PL |
| ADR-04 | Accepted: relative 24-month roadmap | Discard old project dates | Record kickoff and capacity changes; PL |
| ADR-05 | Accepted: NetBird reference/optional adapter, no initial fork | Own product/IP while reusing mature connectivity | Documented unmet requirement and funded maintenance; PS |
| ADR-06 | Accepted: isolated EU-managed customer stacks | Simple initial trust and operational boundary | Measured fleet cost and funded multi-tenancy security work; PS |
| ADR-07 | Accepted: modular API/workers/PostgreSQL | Minimise early infrastructure overhead | Measured throughput/durability need; PS |
| ADR-08 | Accepted: web-first, software appliance before hardware | Reduce supported surface and inventory risk | Offline/install requirements or partner-funded hardware need; PL/PS |
| ADR-09 | Accepted: local raw telemetry/minimised central evidence | Resolve data-lake versus privacy conflict | Purpose-based customer review; PS |
| ADR-10 | Accepted: learning/security purpose separation | Avoid employee ranking and unintended access consequences | No automatic expansion; PL/legal reviewer |
| ADR-11 | Accepted: deterministic approval/tool policy outside models | Model output is not authority | Stronger verified policy mechanism; PS |
| ADR-12 | Accepted: internal agent workspace first | Learn from bounded real tasks before commercialisation | R6/customer evidence; RL |
| ADR-13 | Accepted: research baseline before feature promotion | Prevent synthetic metrics becoming production claims | R0–R6 promotion evidence; RL/PS |
| ADR-14 | Default: Apache-2.0 for original community components | Useful adoption and research reuse | IP/upstream compatibility review before publication; PL |
| ADR-15 | Accepted: GA assessed at every product release | Production maturity cannot wait for final integration | No waiver of critical controls; PS |
| ADR-16 | Accepted: source documents and portal preserved | Maintain history and avoid unrequested migration | Separate authorised portal import; PL |
## External validations, with safe defaults
| Item | Owner and deadline | Default until resolved |
|---|---|---|
| Named team and kickoff | PL, before first sprint | Relative schedule; no claims about current capacity |
| Pilot identity provider and event access | PS/PL, before customer integration | OIDC-capable staging IdP and synthetic/exported fixtures; no live access assumed |
| EU host, region, processing terms and cost | PS, before provisioning | No provider purchase; specified isolated architecture |
| NetBird commercial terms where needed | PL, before paid upstream capability is sold | Community lab only; no HA/SCIM/traffic-streaming promise |
| DPIA/legal role and product applicability | PL, before affected processing/shipment | Minimise data and exclude uncertain high-impact feature |
| Model licence/hardware | RL, before adoption | Benchmark candidates on permitted data; no GPU purchase |
| Community/proprietary licence boundary | PL, before publication | Keep original ownership/notices; publish nothing automatically |
| Independent assessment provider | PS, before GA | Gate remains pending until assessment/retests complete |
## Updating decisions
A change records the problem, evidence, considered alternatives, selected approach, owner, date, consequences, migration plan and affected contracts/gates. Preserve superseded entries. Changes in framework fashion or model rankings alone do not justify a platform migration.

## Slide 6
Four products and their release windows
Product | Production target | Customer outcome
Human Firewall | Months 3–6 | Learning and reporting behaviour
Security Operations | Months 10–12 | Exposure, findings and guided response
Defense Box and Validation | Months 16–18 | Local monitoring and repeatable checks
Agent Security | Months 22–24 | Agent authority and execution evidence
Targets depend on release evidence and capacity. Months start at kickoff.
06
Notes: Four products and their release windows
Human Firewall / Months 3–6 / Learning and reporting behaviour
Security Operations / Months 10–12 / Exposure, findings and guided response
Defense Box and Validation / Months 16–18 / Local monitoring and repeatable checks
Agent Security / Months 22–24 / Agent authority and execution evidence
Project documentation: implementation-plan/08-roadmap-backlog.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.

## Slide 7
Customers and product buyers
Product | Initial buyer | Daily user
Human Firewall | SME owner or IT administrator | Employees and training administrator
Security Operations | IT owner or service partner | Investigator and operator
Defense Box | Infrastructure owner or IT provider | Local infrastructure operator
Agent Security | Engineering or security lead | Developers and agent operators
Initial segment hypothesis: Portuguese SMEs with 20–200 employees.
07
Notes: Customers and product buyers
Human Firewall / SME owner or IT administrator / Employees and training administrator
Security Operations / IT owner or service partner / Investigator and operator
Defense Box / Infrastructure owner or IT provider / Local infrastructure operator
Agent Security / Engineering or security lead / Developers and agent operators
Project documentation: implementation-plan/01-portfolio-strategy.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.

## Slide 8
What success means
Customer value
Users complete the intended workflow and buyers see enough value to renew.
Operational reliability
The team can deploy, support, upgrade and restore each supported product.
Research quality
Claims trace to datasets, methods and reproducible results.
Sustainable delivery
Measured support and infrastructure costs fit the commercial offer.
08
Notes: What success means
Customer value: Users complete the intended workflow and buyers see enough value to renew.
Operational reliability: The team can deploy, support, upgrade and restore each supported product.
Research quality: Claims trace to datasets, methods and reproducible results.
Sustainable delivery: Measured support and infrastructure costs fit the commercial offer.
Project documentation: implementation-plan/01-portfolio-strategy.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.

## Slide 9
Human Firewall
A short learning cycle with clear feedback and useful reporting.
Administrator
Assign a role-relevant programme and review completion evidence.
Learner
Complete a scenario, understand the answer and optionally give feedback.
Recommendation
Use transparent rules based on skills and stated difficulty or relevance.
Delivery
Responsive Portuguese web experience with resumable progress.
09
Notes: Human Firewall
A short learning cycle with clear feedback and useful reporting.
Administrator: Assign a role-relevant programme and review completion evidence.
Learner: Complete a scenario, understand the answer and optionally give feedback.
Recommendation: Use transparent rules based on skills and stated difficulty or relevance.
Delivery: Responsive Portuguese web experience with resumable progress.
Project documentation: implementation-plan/products/01-human-firewall.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://www.sysnet.ucsd.edu/~voelker/pubs/phishtrain-oakland25.pdf
DETAILED PROJECT REFERENCE
# Product 1: Human Firewall
[Index](../README.md) · Owner: Application Engineer; accountable: Product Lead · Target: pilot by month 3, production in months 4–6
## Purpose and customer journey
An SME administrator invites learners, selects a role-relevant programme, reviews aggregate progress and exports evidence. A learner completes a short scenario, receives an explanation, optionally reports difficulty or relevance, and receives a transparent next recommendation. The product remains usable when model services are unavailable.
Initial content covers phishing/reporting, MFA and account protection, safe information handling, and incident reporting. Deliver at least 12 reviewed Portuguese scenarios, including three interactive scenarios in the pilot baseline. Use a responsive web interface with keyboard navigation, readable feedback, resumable progress and no mandatory 3D/native application.
## Release scope
- Organisation roles: administrator, content reviewer and learner; scoped service-operator support access.
- Versioned content and assignments, progress, knowledge checks, completion records and report export.
- Supportive achievements and personal progress; no public individual risk leaderboard, punitive streak or personality scoring.
- Rule-based recommendation from demonstrated skills and explicit feedback, with a visible reason and manual reassignment.
- Aggregate reporting and individual assignment completion for authorised administrators; detailed feedback restricted by purpose.
- Pilot assessment and optional benign phishing exercises only under a separate agreed scope; ordinary training is the default.
Training outcomes never automatically change network access. Models may draft content, but a reviewer approves it before publication. No unrestricted live-generated lessons or instructions are sent to employees.
## Implementation backlog
| ID | Deliverable | Dependency | Acceptance evidence |
|---|---|---|---|
| HF-01 | Content taxonomy and first three scenarios | PL interviews, WP3 | Reviewed Portuguese content; clear learning objective and answer rationale |
| HF-02 | Learner/admin journeys and accessible UI | CORE-01, HF-01 | End-to-end assign → learn → feedback → report test |
| HF-03 | Content/assignment versioning and outcome schema | CORE-02 | Historical completion remains linked to the content actually seen |
| HF-04 | Transparent recommendation rules | HF-03, R1 protocol | Same valid inputs produce an explained recommendation; missing data falls back to baseline |
| HF-05 | Reporting/export and privacy controls | CORE-01/02 | Tenant isolation, authorised completion view, small-group disclosure review |
| HF-06 | Twelve-scenario programme and pilot onboarding | HF-01/02 | Content/security review and administrator walkthrough |
| HF-07 | Production hardening and evidence pack | HF-02–06, CORE-03–05 | G2 criteria and customer support runbooks passed |
## Evaluation and release
Pilot with 3–5 recruited organisations as a target, not an assumption of existing customers. Use R1 to compare static versus adapted recommendations. Primary learning endpoint is delayed knowledge retention; operational measures include reporting behaviour, completion and administrator effort. Record missing follow-up and participant burden. Do not infer causal efficacy from a small uncontrolled pilot.
G1: complete journeys, correct assignment isolation, usable content, recoverable database, monitoring and pilot privacy terms. G2: independent security review, critical/high findings resolved, restore/upgrade evidence, accessible principal workflows, all scenarios reviewed, and support ownership. Pricing/renewal evidence is assessed separately from technical readiness.
After G2, allocate maintenance/content updates within the portfolio support allowance; do not extend the primary development stream indefinitely. New adaptive ML requires the same evidence gate as other research features.
## Research context
Large field evidence finds limited benefit from some common training formats, supporting measured comparison rather than an assumed risk-reduction percentage. [Original phishing-training study](https://www.sysnet.ucsd.edu/~voelker/pubs/phishtrain-oakland25.pdf). The product's initial promise is usable learning and reporting workflows; demonstrated efficacy is a research outcome to establish.

## Slide 10
Human Firewall release scope
Included | Boundary
12 reviewed Portuguese scenarios | Three interactive scenarios support the pilot baseline
Assignments, outcomes and reports | Content versions stay linked to historical completion
Personal progress and achievements | No public individual risk leaderboard or personality scoring
Rule-based adaptation | Learning results never automatically change network access
10
Notes: Human Firewall release scope
12 reviewed Portuguese scenarios / Three interactive scenarios support the pilot baseline
Assignments, outcomes and reports / Content versions stay linked to historical completion
Personal progress and achievements / No public individual risk leaderboard or personality scoring
Rule-based adaptation / Learning results never automatically change network access
Project documentation: implementation-plan/products/01-human-firewall.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://www.sysnet.ucsd.edu/~voelker/pubs/phishtrain-oakland25.pdf

## Slide 11
Human Firewall implementation sequence
Work | Task IDs | Completion evidence
Content and learner journey | HF-01–03 | Reviewed scenarios and complete assignment flow
Adaptation and reports | HF-04–05 | Explained recommendations and authorised exports
Pilot onboarding | HF-06 | Reviewed programme and administrator walkthrough
Production hardening | HF-07 | Security, recovery and support requirements pass
Target 3–5 paid pilot organisations. Recruitment remains unconfirmed.
11
Notes: Human Firewall implementation sequence
Content and learner journey / HF-01–03 / Reviewed scenarios and complete assignment flow
Adaptation and reports / HF-04–05 / Explained recommendations and authorised exports
Pilot onboarding / HF-06 / Reviewed programme and administrator walkthrough
Production hardening / HF-07 / Security, recovery and support requirements pass
Project documentation: implementation-plan/products/01-human-firewall.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://www.sysnet.ucsd.edu/~voelker/pubs/phishtrain-oakland25.pdf

## Slide 12
Security Operations
A traceable investigation connects exposure to remediation.
Observe
Import assets, software components and selected security events.
Prioritise
Show exposure context, source freshness and the basis for each finding.
Investigate
Record evidence, ownership, notes and a guided response plan.
Verify
Track remediation and preserve evidence supporting closure.
12
Notes: Security Operations
A traceable investigation connects exposure to remediation.
Observe: Import assets, software components and selected security events.
Prioritise: Show exposure context, source freshness and the basis for each finding.
Investigate: Record evidence, ownership, notes and a guided response plan.
Verify: Track remediation and preserve evidence supporting closure.
Project documentation: implementation-plan/products/02-security-operations.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://cyclonedx.org/specification/overview/
https://osv.dev/
DETAILED PROJECT REFERENCE
# Product 2: Security Operations
[Index](../README.md) · Owner: Platform/Security Lead · Target: pilot months 7–9, production months 10–12
## Purpose and first workflow
Help a small IT team connect exposure to action: import assets and an SBOM, enrich software vulnerabilities, inspect evidence and uncertainty, prioritise a finding, assign remediation, and verify closure. The product works without the training module. It is not a replacement promise for a staffed 24/7 SOC.
## First-release boundaries
Start with customer inventory import, CycloneDX JSON SBOM ingestion, OSV advisory enrichment and one supported security-event connector. Default connector implementation is Wazuh JSON alert ingestion; use exported sample records before requesting live access. If the pilot cannot provide this source, use documented file ingestion rather than building several new connectors simultaneously.
Asset discovery begins with imports and observed metadata. Active discovery is a separately scoped action. Maintain source/last-seen/confidence fields and resolve conflicting asset identities through review rather than silently merging unrelated devices.
Prioritisation uses transparent rules: asset criticality, exposure evidence, advisory severity and available exploitation context. Unknown reachability remains unknown. Show feed freshness and the evidence behind a recommendation; do not assume a package is exploitable solely because it appears in an SBOM. [CycloneDX](https://cyclonedx.org/specification/overview/), [OSV](https://osv.dev/).
Support finding triage, investigator notes, case linkage, remediation assignments, and three guided playbooks: suspicious authentication review, vulnerable dependency remediation, and suspected phishing response. Initial execution produces a reviewed action plan or export; automated account/endpoint changes require the shared approval executor and a tested target integration.
## Implementation backlog
| ID | Deliverable | Dependency | Acceptance evidence |
|---|---|---|---|
| SO-01 | Asset and SBOM ingestion | CORE-02; customer samples | Versioned validation, malformed input rejection, deduplication, provenance |
| SO-02 | Advisory enrichment and prioritisation | SO-01 | Known fixture findings, stale-feed warning, unknown-reachability handling |
| SO-03 | Wazuh alert/file connector | CORE-02; connector access | Normalisation, last-seen, loss/duplicate accounting and scoped credentials |
| SO-04 | Finding/evidence UI and investigation workflow | SO-01–03 | Evidence lineage, access controls, assignment and closure history |
| SO-05 | Three guided response playbooks | SO-04; CORE-04 | Parameter-bound approval where actions execute; no automatic production containment |
| SO-06 | Evaluated correlation/rule baseline | R2 baseline; SO-03 | Precision and alerts/day measured with labelled cases; no synthetic-label fallback |
| SO-07 | Product operations and release | SO-01–06 | G4 security/load/recovery gates and supported-source documentation |
## Tests and commercial gate
Test duplicate/out-of-order observations, collector clock skew, malformed SBOMs, feed outages, asset identity collision, unauthorised evidence references, stale approved actions, partial remediation and repeated execution after a lost response. Customer trials must report useful findings and false alerts per investigator-day, not accuracy alone.
G3 requires a customer to complete the exposure-to-remediation journey with evidence. G4 requires a documented alert workload the customer's named operator can handle, reliable ingestion at twice the agreed pilot peak, a 48-hour soak run, independent security assessment and tested recovery. Volume limits are measured and published for the supported deployment; do not copy the old 10,000-user target without demand.
## Later capabilities
UEBA, graphs and multimodal fusion remain shadow-mode research until they improve operational utility. Approved containment, repository remediation proposals, ticketing integrations and richer identity sources are extensions after the initial workflows prove useful. Research inference must not leak learning-profile data into employee risk rankings.

## Slide 13
Security Operations first release
Capability | Initial implementation
Inventory and software | Customer imports and CycloneDX JSON SBOM ingestion
Advisory enrichment | OSV adapter with freshness and provenance
Security events | Wazuh JSON alert ingestion or documented file imports
Response | Guided authentication, dependency and phishing playbooks
Unknown reachability stays unknown. A vulnerable component does not alone prove exploitability.
13
Notes: Security Operations first release
Inventory and software / Customer imports and CycloneDX JSON SBOM ingestion
Advisory enrichment / OSV adapter with freshness and provenance
Security events / Wazuh JSON alert ingestion or documented file imports
Response / Guided authentication, dependency and phishing playbooks
Project documentation: implementation-plan/products/02-security-operations.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://cyclonedx.org/specification/overview/
https://osv.dev/

## Slide 14
Security Operations backlog and gates
Work | Task IDs | Acceptance
Ingestion and enrichment | SO-01–03 | Validation, deduplication, loss and source-age visibility
Investigation and response | SO-04–05 | Evidence access and parameter-bound approvals
Detection baseline | SO-06 | Precision and alert burden on labelled cases
Supported release | SO-07 | Recovery, load tests and independent review
14
Notes: Security Operations backlog and gates
Ingestion and enrichment / SO-01–03 / Validation, deduplication, loss and source-age visibility
Investigation and response / SO-04–05 / Evidence access and parameter-bound approvals
Detection baseline / SO-06 / Precision and alert burden on labelled cases
Supported release / SO-07 / Recovery, load tests and independent review
Project documentation: implementation-plan/products/02-security-operations.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://cyclonedx.org/specification/overview/
https://osv.dev/

## Slide 15
Defense Box and Validation
Local monitoring and controlled verification in a software appliance.
Deployment
Supported Linux VM or container on customer infrastructure.
Passive observation
Evaluate Zeek metadata and Suricata alerts with bounded local storage.
Own-product work
Enrolment, health, normalisation, evidence reports and remediation retests.
Expansion
Custom hardware and industrial deployment follow measured demand and safety review.
15
Notes: Defense Box and Validation
Local monitoring and controlled verification in a software appliance.
Deployment: Supported Linux VM or container on customer infrastructure.
Passive observation: Evaluate Zeek metadata and Suricata alerts with bounded local storage.
Own-product work: Enrolment, health, normalisation, evidence reports and remediation retests.
Expansion: Custom hardware and industrial deployment follow measured demand and safety review.
Project documentation: implementation-plan/products/03-defense-box.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://github.com/apache/caldera
https://attack.mitre.org/tactics/ics/
https://attack.mitre.org/mitigations/ics/
DETAILED PROJECT REFERENCE
# Product 3: Defense Box and Validation
[Index](../README.md) · Owner: Platform/Security Lead · Target: pilot months 13–15, production months 16–18
## Purpose and deployment
A software appliance observes approved network metadata locally, reports evidence-backed findings, and runs separately authorised validation exercises in a controlled environment. Start with a supported Linux virtual machine/container deployment on customer-provided infrastructure. Custom hardware manufacturing and a universal endpoint-protection agent are outside the first release.
Keep passive collection and active validation in distinct execution boundaries. Passive sensor connectivity must not automatically grant an active runner access to the same targets. Local storage is encrypted and bounded; packet payload collection is disabled by default. A customer chooses the interface, observation scope and retention before enabling collection.
## Components and own-product work
Evaluate Zeek metadata and Suricata alerts using fixed replay datasets. Reuse maintained sensors; build the AegisAI deployment management, normalisation, evidence correlation, health diagnostics, reporting and remediation-verification workflow. Test a maintained adversary-emulation runner in the lab through an adapter; the current historical MITRE Caldera repository redirects to Apache Caldera, so pin its actual repository and licence at adoption. [Current repository](https://github.com/apache/caldera).
The first validation library contains five benign, reproducible checks: sensor/alert pipeline verification, approved service reachability, denied-route verification, known test-file detection in an isolated endpoint, and backup-restore exercise evidence. Expand only through reviewed test definitions. No live malware creation, broad autonomous exploitation, or unbounded discovered-target expansion is required for the product.
## Execution contract
Each plan names an authorising customer, exact targets, allowed techniques, time window, rate/resource limits, expected side effects, abort mechanism and cleanup procedure. The runner validates scope before each step and blocks changed/out-of-scope targets. A lost control connection stops new active steps. Report partial execution and cleanup failure explicitly. A model may draft a test plan; it cannot authorise one.
## Implementation backlog
| ID | Deliverable | Dependency | Acceptance evidence |
|---|---|---|---|
| DB-01 | Appliance packaging and health | CORE-03/05; SO contracts | Install, enrol, observe health, revoke and uninstall without residual access |
| DB-02 | Passive sensor adapters and local buffer | DB-01 | Loss counts, bounded disk use, no payload export by default |
| DB-03 | Scoped validation runner | CORE-04; isolated lab | Reject out-of-scope targets, expire approval, abort and clean up |
| DB-04 | Five-check library and reports | DB-02/03; R4 | Reproducible expected result and verified remediation retest |
| DB-05 | Local inference comparison | R5; DB-02 | Quality/resource benchmark; rule-only operation when model unavailable |
| DB-06 | Release and support package | DB-01–05 | G6 gates, hardware/VM support matrix and operator recovery exercise |
## Acceptance and industrial path
Measure CPU, memory, disk, packet loss and processing delay on the published reference profile. Test disk exhaustion, sensor crash, clock skew, revoked enrolment, interrupted update, traffic spikes and tampered configuration. Publish measured throughput rather than borrowing upstream maximum claims.
G5 requires stable passive collection and fully scoped execution in an agreed pilot. G6 requires independent assessment, safe abort/cleanup, repeatable installation/rollback and supportable overhead. A failed abort or scope-enforcement test blocks release.
OT begins with lab traces and passive inventory mappings. An industrial pilot needs an operator sponsor, approved topology, process-safety review and change window. No active scanning or inline enforcement on industrial controllers by default. ATT&CK for ICS provides threat/asset vocabulary, not permission to run techniques. [ICS tactics](https://attack.mitre.org/tactics/ics/), [ICS mitigations](https://attack.mitre.org/mitigations/ics/).

## Slide 16
Validation execution boundaries
Required before a run | Behaviour during and after a run
Named customer authoriser | The runner checks authority and expiry
Exact targets and allowed techniques | Discovery cannot silently expand the approved scope
Time and resource limits | Abort stops new steps on a safety trigger or lost control
Expected effects and cleanup | The report records partial execution and cleanup failures
Passive sensor access never automatically grants active testing authority.
16
Notes: Validation execution boundaries
Named customer authoriser / The runner checks authority and expiry
Exact targets and allowed techniques / Discovery cannot silently expand the approved scope
Time and resource limits / Abort stops new steps on a safety trigger or lost control
Expected effects and cleanup / The report records partial execution and cleanup failures
Project documentation: implementation-plan/products/03-defense-box.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://github.com/apache/caldera
https://attack.mitre.org/tactics/ics/
https://attack.mitre.org/mitigations/ics/

## Slide 17
Defense Box implementation sequence
Work | Task IDs | Acceptance
Packaging and passive data | DB-01–02 | Install, enrol, bound disk use and report loss
Validation and reports | DB-03–04 | Five safe checks, abort, cleanup and retest evidence
Local inference | DB-05 | Measured quality and resource use against rules
Supported release | DB-06 | Reference profile, rollback and operating guide
17
Notes: Defense Box implementation sequence
Packaging and passive data / DB-01–02 / Install, enrol, bound disk use and report loss
Validation and reports / DB-03–04 / Five safe checks, abort, cleanup and retest evidence
Local inference / DB-05 / Measured quality and resource use against rules
Supported release / DB-06 / Reference profile, rollback and operating guide
Project documentation: implementation-plan/products/03-defense-box.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://github.com/apache/caldera
https://attack.mitre.org/tactics/ics/
https://attack.mitre.org/mitigations/ics/

## Slide 18
Agent Security
Task-level authority controls agents across runtimes.
Administrator
Register a workload and assign tool, resource and budget policies.
Developer
Use a documented gateway and small SDK with existing agent runtimes.
Operator
Inspect actions, revoke capabilities and reconcile interrupted runs.
First workflows
Sandboxed repository maintenance and evidence-based report drafting.
18
Notes: Agent Security
Task-level authority controls agents across runtimes.
Administrator: Register a workload and assign tool, resource and budget policies.
Developer: Use a documented gateway and small SDK with existing agent runtimes.
Operator: Inspect actions, revoke capabilities and reconcile interrupted runs.
First workflows: Sandboxed repository maintenance and evidence-based report drafting.
Project documentation: implementation-plan/products/04-agent-security.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://arxiv.org/abs/2602.16901
https://arxiv.org/abs/2602.22769
https://arxiv.org/abs/2608.22868
DETAILED PROJECT REFERENCE
# Product 4: Agent Security
[Index](../README.md) · Owner: Platform/Security Lead; research: Research Lead · Target: external pilot months 19–21, production months 22–24
## Product purpose
Give engineering and security teams enforceable control over an agent's identity, tools, resources, model use and execution evidence. Productise lessons from the internal workspace only after separate customer discovery. This is a governance/execution product, not a promise to build a frontier foundation model or a general autonomous employee.
An administrator registers an agent workload, assigns a task-scoped policy and budget, runs an approved workflow, inspects evidence, and revokes authority when necessary. Developers integrate through documented APIs and a small SDK; existing agent runtimes remain usable.
## Authority boundaries
- Human identity, workload identity, execution instance and network peer are distinct records.
- Typed tool policies restrict operation, target and parameters. Network access alone never authorises a tool call.
- Untrusted retrieved content and tool outputs cannot grant permissions or rewrite policy.
- A deterministic gateway checks capabilities independently of model-generated risk assessments.
- Provider keys remain in the gateway/secret store; workers receive short-lived, scoped credentials where possible.
- Sandboxes use dedicated worker VMs with unprivileged task containers and controlled egress; no host socket or production secret mounts.
- Budget exhaustion stops new calls; interrupted runs retain evidence and require reconciliation for uncertain side effects.
- Replay is read-only reconstruction by default, not repeated execution.
## Initial supported workflows
Support one sandboxed repository-maintenance workflow and one evidence-retrieval/report-drafting workflow. Permit read-only source access and reviewed patch export; deployment and external publication are separate approved actions. Native computer/browser automation remains an optional isolated tool, not an unrestricted desktop session.
## Implementation backlog
| ID | Deliverable | Dependency | Acceptance evidence |
|---|---|---|---|
| AS-01 | Workload identity and policy service | CORE-01/04; internal workspace | Scoped issue/revoke, task binding and denied cross-workload access |
| AS-02 | Tool gateway and SDK | AS-01; interface contracts | Parameter validation, capability denial, approval binding and conformance tests |
| AS-03 | Sandboxed execution and egress | AS-02; DB packaging lessons | No host/secret escape in test suite; blocked unapproved destinations |
| AS-04 | Model access and cost controls | Workspace benchmarks | Provider routing respects data class, model allowlist, hard budget and timeout |
| AS-05 | Audit/checkpoint/recovery | AS-02–04 | Reconstruct decisions and partial effects; no duplicated actions after restart |
| AS-06 | Customer integrations and release | AS-01–05; R6 | Two supported workflows, independent assessment, G8 evidence and support guide |
## Research-to-product gate
Evaluate clean-task success alongside policy-violation rate, attempted exfiltration success, injection persistence, memory poisoning, revocation delay, latency and cost. Test attacks in retrieved pages, repository files, tool output and stored memory. Report denominator, task distribution, model/runtime revisions and residual failures; a zero count in a finite benchmark is not proof of universal safety.
AgentLAB informs long-horizon adversarial evaluation; AMA-Bench informs memory experiments; AgentFlow informs data-flow enforcement hypotheses. They do not establish production readiness of AegisAI. [AgentLAB](https://arxiv.org/abs/2602.16901), [AMA-Bench](https://arxiv.org/abs/2602.22769), [AgentFlow](https://arxiv.org/abs/2608.22868).
G7 requires external users to complete supported workflows under enforced policy. G8 requires no unresolved critical/high assessment findings, tested isolation and revocation, recovery and cost accounting, and a documented compatibility matrix. Multiple collaborating agents are a later supported configuration only after outperforming the simpler baseline at acceptable cost and containment.

## Slide 19
Agent authority and execution
Boundary | Design decision
Identity | Separate human, workload, run and network-peer identities
Permission | A deterministic gateway checks operation, target and parameters
Isolation | Dedicated worker VM, unprivileged task container and controlled egress
Evidence | Persist checkpoints and audit traces without replaying side effects
Models propose actions. Authorised people and deterministic policies govern consequential execution.
19
Notes: Agent authority and execution
Identity / Separate human, workload, run and network-peer identities
Permission / A deterministic gateway checks operation, target and parameters
Isolation / Dedicated worker VM, unprivileged task container and controlled egress
Evidence / Persist checkpoints and audit traces without replaying side effects
Project documentation: implementation-plan/products/04-agent-security.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://arxiv.org/abs/2602.16901
https://arxiv.org/abs/2602.22769
https://arxiv.org/abs/2608.22868

## Slide 20
Agent Security backlog and release
Work | Task IDs | Acceptance
Identity and tools | AS-01–02 | Scoped issue/revoke and denied unauthorised calls
Sandbox and model gateway | AS-03–04 | Secret isolation, approved routes and hard budgets
Recovery and audit | AS-05 | No duplicated action after interruption
Customer release | AS-06 | Two workflows, compatibility matrix and security review
20
Notes: Agent Security backlog and release
Identity and tools / AS-01–02 / Scoped issue/revoke and denied unauthorised calls
Sandbox and model gateway / AS-03–04 / Secret isolation, approved routes and hard budgets
Recovery and audit / AS-05 / No duplicated action after interruption
Customer release / AS-06 / Two workflows, compatibility matrix and security review
Project documentation: implementation-plan/products/04-agent-security.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://arxiv.org/abs/2602.16901
https://arxiv.org/abs/2602.22769
https://arxiv.org/abs/2608.22868

## Slide 21
Shared platform architecture
Functional area | Responsibilities
Customer applications | Learning, findings, investigations, validation and agent administration
Platform services | Identity, roles, approvals, configuration, entitlements and audit
Evidence and intelligence | Assets, observations, findings, models and provenance
Edge and execution | Collectors, local inference and isolated runners
Delivery infrastructure | Packaging, secrets, monitoring, backups and recovery
Logical areas can share a deployment. They do not require five microservices.
21
Notes: Shared platform architecture
Customer applications / Learning, findings, investigations, validation and agent administration
Platform services / Identity, roles, approvals, configuration, entitlements and audit
Evidence and intelligence / Assets, observations, findings, models and provenance
Edge and execution / Collectors, local inference and isolated runners
Delivery infrastructure / Packaging, secrets, monitoring, backups and recovery
Project documentation: implementation-plan/03-shared-architecture.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://cyclonedx.org/specification/overview/
https://osv.dev/
DETAILED PROJECT REFERENCE
# Shared architecture
[Index](README.md) · Specification, not deployed software · Owner: Platform/Security Lead
## Deployment and ownership
Start with a customer-isolated EU Linux deployment: React/TypeScript web application, Python/FastAPI modular API, PostgreSQL, object storage, and asynchronous workers. Use OIDC for customer identity; application authorisation is independent of the identity provider. Use container images and infrastructure-as-code. A PostgreSQL-backed job queue/outbox is sufficient initially; do not add a message broker or distributed workflow engine without an observed requirement.
One customer stack contains its own application database, storage namespace/credentials, encryption boundary and optional NetBird deployment. Shared fleet administration stores deployment health and billing metadata only. Cross-customer administrative access requires time-bounded elevation and an audit trail. Production, staging and research use different credentials and networks.
```mermaid
flowchart TD
User[Customer user or administrator] --> UI[AegisAI web applications]
UI --> API[Identity, permissions and product API]
API --> DB[Customer PostgreSQL and evidence storage]
API --> Jobs[Persistent jobs and approvals]
Jobs --> Adapter[Versioned tool and connectivity adapters]
Adapter --> Edge[Customer edge service]
Edge --> Local[Local telemetry, sensors and optional inference]
Edge --> Ingest[Minimised authenticated event ingestion]
Ingest --> DB
IdP[OIDC identity provider] --> API
Net[Optional NetBird transport] -. connectivity .-> Edge
Lab[Isolated research and simulation environment] --> Export[Reviewed artefact promotion]
Export --> API
```
The diagram shows logical connections, not permission to make every route bidirectional. Edge ingestion is outbound initiated. A sensor interface must not become a route from a sandbox to customer production.
## Product modules
Learning manages content, assignments and outcomes. Operations manages assets, components, observations, findings and investigations. Validation manages scoped test plans and results. Agent Security manages workload identity, tool policy and execution. Shared services handle organisations, audit, approvals, entitlements, evidence references and jobs. Disabling one product must not break another's login, evidence access or scheduled processing.
## Data flow and minimisation
1. An enrolled source authenticates with a revocable workload credential, never an administrator token.
2. A collector validates and classifies records locally, removing prohibited fields before export.
3. Ingestion validates a versioned envelope, deduplicates by producer/event identity, stores provenance and acknowledges durable receipt.
4. Rules or evaluated models produce findings with evidence references and model/rule versions.
5. An authorised user reviews a proposed action. Execution checks approval scope and current target state immediately before acting.
6. A follow-up observation records success, failure, uncertainty or required manual recovery.
Default handling: raw packet payloads disabled; locally buffered metadata expires after seven days; centrally stored operational observations expire after 30 days; findings/audit after 180 days; learning outcomes after 180 days. These are pilot design defaults, configurable through a documented customer-purpose/retention review. Research copies require separate approval and retention. Pseudonymisation is not anonymisation. Backup expiry and restore-time deletion replay are covered in the [privacy specification](11-security-privacy-regulation.md).
## Build, reuse and defer
| Capability | Initial decision | Reason/revisit trigger |
|---|---|---|
| Evidence/finding model, UX, workflows | Build | Own-product differentiation |
| Networking | Optional upstream NetBird behind adapter | Avoid bespoke tunnel/security maintenance; revisit only for a measured gap |
| Authentication | OIDC integration | Separate authentication from authorisation; pilot IdP selected from actual customer environment |
| SCA | CycloneDX JSON ingestion + OSV enrichment adapter | Reuse standards and advisories; preserve provenance and freshness |
| Network monitoring | Evaluate Zeek metadata and Suricata alerts in lab | Reuse sensors; AegisAI owns normalisation and findings |
| Workflow | Persistent jobs, retries, outbox and approval records | Introduce Temporal only if durable workflow complexity exceeds this implementation |
| Observability | OpenTelemetry instrumentation; standard metrics/log collection | Correlate execution without logging secrets or full prompts by default |
| Model serving | Adapter; local runtime benchmark before selection | No unverified GPU purchase or latency promise |
| User interface | Responsive web first | Native mobile/Electron only for demonstrated unmet workflows |
| Storage/scale | PostgreSQL and object storage | No data lake, Kafka or Kubernetes as a release prerequisite |
Standards/provider context: [CycloneDX](https://cyclonedx.org/specification/overview/), [OSV](https://osv.dev/). Pin versions and verify licences in the implementation change that adopts each dependency.
## Failure and security boundaries
- Queue interruption: resume persisted jobs; require idempotency or reconciliation for external side effects. Never blindly retry an uncertain account-disable operation.
- Collector offline: bounded local buffer, visible last-seen timestamp, no fabricated normal status; overflow records a loss count.
- Model unavailable: deterministic baseline/reporting continues; mark model-generated enrichment unavailable.
- External feed stale: show age and last success; missing advisories are not evidence of no vulnerabilities.
- Compromised agent: isolate execution, revoke credentials, preserve audit, disable tool capability without disabling unrelated customer networking.
- Network management outage: expose stale policy state; do not promise immediate revocation until enforcement is confirmed.
- Storage pressure: stop optional capture first; preserve audit integrity and alert the operator.
Platform tests cover cross-organisation references, duplicate events, schema mismatch, stale credentials, interrupted upgrades and backup restoration. Concrete gate evidence is defined in the [production handbook](12-production-handbook.md).

## Slide 22
Evidence and action flow
Stage | System behaviour
1 Collect | Authenticate the source and minimise data locally
2 Ingest | Validate, deduplicate and acknowledge durable receipt
3 Analyse | Produce a finding with rule/model version and evidence
4 Review and execute | Check approval, scope and current target state
5 Reconcile | Record success, uncertainty or required recovery
22
Notes: Evidence and action flow
1 Collect / Authenticate the source and minimise data locally
2 Ingest / Validate, deduplicate and acknowledge durable receipt
3 Analyse / Produce a finding with rule/model version and evidence
4 Review and execute / Check approval, scope and current target state
5 Reconcile / Record success, uncertainty or required recovery
Project documentation: implementation-plan/03-shared-architecture.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://cyclonedx.org/specification/overview/
https://osv.dev/

## Slide 23
Build, reuse and defer
Build in AegisAI | Reuse behind interfaces | Add only when justified
Evidence and product workflows | OIDC and mature networking | Additional orchestration engines
Customer experience | Sensors and advisory sources | Kafka or a large data lake
Approval and reconciliation | Model-serving runtimes | Kubernetes and service mesh
Operational lifecycle | Standard observability tools | Native apps and custom hardware
23
Notes: Build, reuse and defer
Evidence and product workflows / OIDC and mature networking / Additional orchestration engines
Customer experience / Sensors and advisory sources / Kafka or a large data lake
Approval and reconciliation / Model-serving runtimes / Kubernetes and service mesh
Operational lifecycle / Standard observability tools / Native apps and custom hardware
Project documentation: implementation-plan/03-shared-architecture.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://cyclonedx.org/specification/overview/
https://osv.dev/

## Slide 24
Deployment and data boundaries
Customer isolation
Separate EU-managed stacks, credentials, storage and backups.
Edge processing
Keep raw sensitive telemetry local where practical. Export permitted evidence.
Product separation
Training and security findings have distinct purposes and access rules.
Fleet operation
Central administration stores health and billing metadata with audited support elevation.
24
Notes: Deployment and data boundaries
Customer isolation: Separate EU-managed stacks, credentials, storage and backups.
Edge processing: Keep raw sensitive telemetry local where practical. Export permitted evidence.
Product separation: Training and security findings have distinct purposes and access rules.
Fleet operation: Central administration stores health and billing metadata with audited support elevation.
Project documentation: implementation-plan/03-shared-architecture.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://cyclonedx.org/specification/overview/
https://osv.dev/

## Slide 25
NetBird technical reference
Component | Purpose | AegisAI consideration
Client / WireGuard | Encrypted peer connectivity | Enrolment and device trust
Management | Identity and network state | Provider adapter and reconciliation
Signal | Connection negotiation | Connectivity diagnostics
Relay / routing peer | Fallback or LAN reachability | Failure domains and onward traffic protection
25
Notes: NetBird technical reference
Client / WireGuard / Encrypted peer connectivity / Enrolment and device trust
Management / Identity and network state / Provider adapter and reconciliation
Signal / Connection negotiation / Connectivity diagnostics
Relay / routing peer / Fallback or LAN reachability / Failure domains and onward traffic protection
Project documentation: implementation-plan/04-netbird-study.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://docs.netbird.io/about-netbird/how-netbird-works
https://docs.netbird.io/manage/networks/how-routing-peers-work
https://docs.netbird.io/selfhosted/enterprise
https://github.com/netbirdio/netbird/blob/main/LICENSE
https://docs.netbird.io/agent-network/how-it-works
https://docs.netbird.io/agent-network
https://docs.netbird.io/agent-network/quickstart
DETAILED PROJECT REFERENCE
# NetBird: technical foundation study and reuse boundary
[Index](README.md) · Checked 18 September 2026 · Owner: Platform/Security Lead
## What to learn
NetBird coordinates authenticated peers using Management, Signal, Relay and device clients. Clients generate WireGuard keys; private keys remain on-device. Management distributes authorised peer/network state. Signal exchanges connection candidates; direct tunnels carry application traffic when possible. Relay provides an encrypted fallback when direct connectivity fails. Policy and DNS handling are applied by clients. The architecture page describes both historical TURN/Coturn and newer relay behaviour, so deployment instructions must match a pinned release rather than combine generations. [Architecture](https://docs.netbird.io/about-netbird/how-netbird-works).
A routing peer forwards overlay traffic to non-client resources. The overlay terminates there; application encryption and LAN segmentation remain separate requirements. NAT/masquerading and return routing affect attribution and reachability. [Routing documentation](https://docs.netbird.io/manage/networks/how-routing-peers-work).
## AegisAI component decisions
| Upstream concept | AegisAI use | Own responsibility |
|---|---|---|
| Peer enrolment | Optional connectivity for edge collectors and internal workers | Asset identity, enrolment approval, revocation workflow |
| Network policy | Transport reachability for approved service paths | Application permissions, tool capabilities and human approvals |
| Management API | Adapter for inventory and proposed configuration changes | Stable product contract, reconciliation and audit |
| Signal/NAT traversal | Upstream implementation where selected | Connectivity diagnostics and support boundary |
| Relay | Fallback for supported edge topology | Capacity, egress cost, availability tests |
| Routing peer | Explicitly scoped access to legacy resources | LAN trust boundary, minimal routes and customer approval |
| Upstream dashboard | Administrator troubleshooting where needed | AegisAI product experience; no rebranding claim of upstream authorship |
Use upstream unmodified binaries initially. Products depend on an AegisAI connectivity interface, not NetBird peer/group IDs. Store provider mappings in the adapter. An HTTPS-only deployment remains possible when overlay connectivity adds no value. A fork requires an ADR documenting gap, upstream contribution attempt, maintenance owner, licensing and upgrade/security burden.
## Operational and commercial limits
Self-hosted NetBird is currently single-account. For isolated customers use separate deployments; groups alone are not a tenant boundary. Commercial self-hosted features include control-plane HA, SCIM and traffic-flow streaming. Cloud prices do not price those licences. Confirm terms for each customer entity before sale.
Direct sessions can survive management downtime, but enrolment and policy updates cannot. A combined-server restart also affects its relay; separating relay changes that failure domain. Enterprise licence validation sends installation metadata/counters, which belongs in the subprocessors/data-flow assessment. These constraints are important to cost and service design. [Enterprise documentation, updated 16 September 2026](https://docs.netbird.io/selfhosted/enterprise).
The repository applies BSD-3-Clause by default with AGPL-covered server directories including management, signal, relay and combined. Inspect all shipped repositories and the exact release, not only the top-level label. API separation is an engineering boundary, not a legal conclusion about derived works. Track notices, modifications, source-offer obligations and any commercial agreement. [Repository licence](https://github.com/netbirdio/netbird/blob/main/LICENSE).
## Agent Network: optional evaluation
NetBird Agent Network distinguishes proxied model calls from direct resource connections. Its proxy can inject provider credentials and apply model/usage policy; direct network connections do not automatically receive request/token accounting. It is beta and the quickstart uses release candidates. [Architecture](https://docs.netbird.io/agent-network/how-it-works), [beta status](https://docs.netbird.io/agent-network), [quickstart](https://docs.netbird.io/agent-network/quickstart).
AegisAI must additionally enforce tool semantics, workload isolation, task-scoped approval and execution evidence. A device identity does not distinguish every process on a shared machine. Separate worker identities and execution boundaries are required. Evaluate Agent Network internally against an independent gateway baseline; it is not a first-product dependency.
## Lab checklist and acceptance
| Test | Evidence required |
|---|---|
| Enrol approved collector; attempt unauthorised enrolment | Allowed/denied identity records, no administrator key on worker |
| Direct connection and forced relay fallback | Packet path, latency, throughput and egress measurement |
| Denied route and DNS behaviour | Negative reachability tests and resolver configuration |
| Revoke peer while online/offline | Measured propagation time and documented stale-state behaviour |
| Restart management and relay independently | Session and onboarding behaviour; maintenance procedure |
| Overlapping customer address ranges | Separate-stack isolation and no accidental routing overlap |
| Rotate credentials and upgrade pinned release | Rollback and retained authorised configuration |
| Attempt agent tool misuse through allowed network route | Application policy still denies the operation |
## Business lesson
NetBird combines a free adoption route with paid operation, organisational features, support and enterprise arrangements. AegisAI should apply the underlying pattern to its own products: useful community components, operationally valuable paid services, and clearly scoped enterprise work. It should not base its margin on an assumed right to resell commercial NetBird functionality. Pricing comparisons and own-product economics are in the [business model](10-market-business-model.md).

## Slide 26
NetBird reuse and product ownership
Optional provider
Use upstream components when they solve a deployment need. Preserve another transport path.
Stable product contracts
Keep NetBird identifiers inside the connectivity adapter.
Ownership
AegisAI owns evidence, intelligence, workflows, UX and lifecycle.
Business lesson
A useful community foundation can support managed operation and enterprise services.
26
Notes: NetBird reuse and product ownership
Optional provider: Use upstream components when they solve a deployment need. Preserve another transport path.
Stable product contracts: Keep NetBird identifiers inside the connectivity adapter.
Ownership: AegisAI owns evidence, intelligence, workflows, UX and lifecycle.
Business lesson: A useful community foundation can support managed operation and enterprise services.
Project documentation: implementation-plan/04-netbird-study.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://docs.netbird.io/about-netbird/how-netbird-works
https://docs.netbird.io/manage/networks/how-routing-peers-work
https://docs.netbird.io/selfhosted/enterprise
https://github.com/netbirdio/netbird/blob/main/LICENSE
https://docs.netbird.io/agent-network/how-it-works
https://docs.netbird.io/agent-network
https://docs.netbird.io/agent-network/quickstart

## Slide 27
NetBird operational constraints
Constraint | Project consequence
Self-hosted single account | Separate customer deployments for isolation
Management outage | Existing traffic and policy-update availability differ
Commercial features | Confirm HA, SCIM and logging terms before sale
Agent Network beta | Internal evaluation only until maturity and need justify adoption
Exact licence, supported release and commercial terms require adoption-time checks.
27
Notes: NetBird operational constraints
Self-hosted single account / Separate customer deployments for isolation
Management outage / Existing traffic and policy-update availability differ
Commercial features / Confirm HA, SCIM and logging terms before sale
Agent Network beta / Internal evaluation only until maturity and need justify adoption
Project documentation: implementation-plan/04-netbird-study.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://docs.netbird.io/about-netbird/how-netbird-works
https://docs.netbird.io/manage/networks/how-routing-peers-work
https://docs.netbird.io/selfhosted/enterprise
https://github.com/netbirdio/netbird/blob/main/LICENSE
https://docs.netbird.io/agent-network/how-it-works
https://docs.netbird.io/agent-network
https://docs.netbird.io/agent-network/quickstart

## Slide 28
Product interfaces
Resource group | Contract responsibility
Identity and assets | Organisation scope, roles, source identity and ownership
Learning and observations | Versioned outcomes, occurrence time and provenance
Findings and evidence | Accessible references, confidence and rule/model version
Collectors and agents | Enrolment, health, capabilities and revocation
Actions and validation | Bounded targets, approval, expiry and execution results
28
Notes: Product interfaces
Identity and assets / Organisation scope, roles, source identity and ownership
Learning and observations / Versioned outcomes, occurrence time and provenance
Findings and evidence / Accessible references, confidence and rule/model version
Collectors and agents / Enrolment, health, capabilities and revocation
Actions and validation / Bounded targets, approval, expiry and execution results
Project documentation: implementation-plan/05-interface-contracts.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
DETAILED PROJECT REFERENCE
# Interface contracts: implementation design baseline
[Index](README.md) · Owner: Platform/Security Lead · Status: proposed v1 contracts, not an implemented API
## Common rules
Use `/api/v1` REST endpoints documented with OpenAPI in the product repository. Derive organisation scope from the authenticated principal; validate any supplied organisation identifier against it. Every object lookup enforces organisation ownership, including references nested inside request bodies. Cursor pagination applies to lists. Timestamps are UTC; retain event occurrence and receipt separately. Changes use optimistic concurrency where a stale state could invalidate an approval.
Mutating requests accept an idempotency key scoped to principal, organisation and operation. Reuse with a different payload returns a conflict. Validation errors are explicit; unsupported schema versions are quarantined or rejected, never silently reinterpreted. Credential material is returned only at creation and excluded from logs.
## Resources and minimum operations
| Resource group | Minimum fields/relationships | Initial operations |
|---|---|---|
| Organisation and identity | Organisation ID, identity type, external subject, role bindings, state | Read configuration; invite/revoke member; inspect own permissions |
| Asset and software component | Asset ID, source identity, last seen, owner; component package identifier/version, SBOM reference | Import/upsert inventory; list assets; attach validated SBOM |
| Learning | Content version, assignment, pseudonymous learner reference, outcome and feedback | Assign; fetch content; submit outcome; report aggregate progress |
| Observation | Producer/event ID, occurrence/receipt time, category, schema version, classified payload, evidence reference | Ingest batch; query authorised records |
| Finding | Evidence references, severity, confidence/limitations, rule/model version, state, assignee | Create; triage; annotate; close with resolution evidence |
| Proposed action | Target, operation, parameter digest, preconditions, expiry, justification, approver, execution state | Propose; approve/reject; execute; reconcile; record recovery |
| Collector | Device identity, configuration version, health, software version, credential state | Enrol; heartbeat; fetch signed configuration; rotate/revoke |
| Validation plan | Explicit targets, allowed techniques, time window, resource limits, authoriser, abort/cleanup policy | Validate scope; approve; run; abort; retrieve findings |
| Agent run | Workload/task identity, policy version, tool scopes, budget, evidence trace, checkpoint | Start; inspect; pause/cancel; revoke capability; export audit |
Product endpoints must not expose internal provider-specific identifiers as the only stable identity. All evidence references include a content hash, storage location accessible through authorisation, provenance and retention class.
## Event envelope example
```json
{
"schema_version": "1.0",
"event_id": "producer-generated-unique-id",
"producer_id": "enrolled-collector-id",
"occurred_at": "2026-09-18T10:00:00Z",
"category": "asset.observed",
"classification": "operational-metadata",
"asset_ref": "asset-id",
"payload": {"source": "inventory-import"}
}
```
The authenticated service supplies organisation context server-side. This example contains no customer data and illustrates the envelope only; category-specific schemas are delivered with their connector. Deduplicate on organisation + producer + event ID. Store receipt time on ingestion. Acknowledgement means durable persistence, not completion of all downstream analysis.
## Asynchronous jobs and action approval
Long-running imports, reports, simulations and model tasks return `202 Accepted` with a job reference. States: queued, running, awaiting approval, succeeded, failed, cancelled, or needs reconciliation. Record attempt history and retry policy. Pure ingestion/report work can retry; irreversible external operations require an idempotent target API or explicit reconciliation before retry.
Approval binds the exact operation, target, parameter digest, policy version and expiry. A changed target state or request invalidates approval. The executor rechecks authorisation immediately before acting. The proposer cannot approve their own high-impact production action. Cancellation is best-effort for in-flight operations and must disclose partial effects. Audit replay reconstructs evidence; it never re-executes side effects by default.
## Adapter contracts
| Adapter | Responsibilities | Must not do |
|---|---|---|
| ConnectivityProvider | Enrol/inspect/revoke transport identity; propose/apply approved reachability changes; report capabilities | Imply network reachability grants application permission |
| ObservationSource | Validate source, normalise records, preserve provenance/freshness and loss counters | Invent labels or suppress ingestion failure |
| ModelProvider | Report model/revision, classify permitted inputs, enforce timeout/budget, record usage | Silently send restricted data to a cloud fallback |
| ToolExecutor | Validate typed input, task capability and approval; isolate execution; return bounded evidence | Accept a model-generated permission claim as authority |
| ValidationRunner | Enforce signed scope, limits, abort and cleanup; collect results | Expand targets from discovered assets without new approval |
## Contract acceptance tests
Test cross-organisation IDs, revoked principals, malformed and oversized payloads, duplicate and out-of-order events, unsupported schema versions, expired approval, changed parameter digest, lost response after successful side effect, cancellation during execution, and unauthorised evidence export. A connector must pass the shared conformance suite before joining a supported release. Additive v1 fields remain optional; breaking changes require a new version and a migration/deprecation plan.

## Slide 29
Jobs, approvals and recovery
Persistent jobs
Long tasks return a job reference and retain attempts and checkpoints.
Bound approval
Approval covers exact operation, target, parameters, policy version and expiry.
Safe retry
External side effects need idempotency or reconciliation before retry.
Versioned contracts
Reject unsupported schemas and deny cross-organisation object references.
29
Notes: Jobs, approvals and recovery
Persistent jobs: Long tasks return a job reference and retain attempts and checkpoints.
Bound approval: Approval covers exact operation, target, parameters, policy version and expiry.
Safe retry: External side effects need idempotency or reconciliation before retry.
Versioned contracts: Reject unsupported schemas and deny cross-organisation object references.
Project documentation: implementation-plan/05-interface-contracts.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.

## Slide 30
Research programme
Track | Question that informs product work
R0 Reproducibility | Which historical results can we independently reproduce?
R1 Human factors | Does adaptation improve useful learning outcomes?
R2–R3 Detection and explanation | Do findings help investigators at an acceptable alert burden?
R4–R5 Validation and local intelligence | Can we test defenses safely and process data effectively?
R6 Agent systems | Can bounded agents complete tasks under enforced authority?
30
Notes: Research programme
R0 Reproducibility / Which historical results can we independently reproduce?
R1 Human factors / Does adaptation improve useful learning outcomes?
R2–R3 Detection and explanation / Do findings help investigators at an acceptable alert burden?
R4–R5 Validation and local intelligence / Can we test defenses safely and process data effectively?
R6 Agent systems / Can bounded agents complete tasks under enforced authority?
Project documentation: implementation-plan/06-research-programme.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://www.sysnet.ucsd.edu/~voelker/pubs/phishtrain-oakland25.pdf
https://www.nist.gov/blogs/cybersecurity-insights/privacy-attacks-federated-learning
DETAILED PROJECT REFERENCE
# Research programme and promotion rules
[Index](README.md) · Owner: Research Lead · All experiments below are planned, not completed
## Shared method
Every experiment has a question, baseline, dataset licence/provenance, preregistered split and metrics, resource budget, versioned configuration and reproducible artefact. Record negative and inconclusive results. Keep synthetic, public benchmark and customer evidence separate. Missing labels fail evaluation; they must never trigger random ground truth. Models and rules used in production require versioned release records and rollback.
Use a fixed exploratory/evaluation split, prevent subject/time leakage, and reserve the final test set before tuning. Report confidence intervals and operational costs, not single accuracy figures. Research participation and product use have separate purposes and permissions. Customer data is not automatically available for model training.
## R0 — Reproducibility and evidence repair, months 1–3
Question: which claims in the local paper and reports can be reproduced from identified inputs?
Inventory the CERT/mock-CERT loaders, fusion experiments, drift experiments and synthetic affective/phishing work. For each reported number record dataset/version, real or generated labels, preprocessing, split, seed, code commit, dependencies, model artefact and output. Trace placeholder-label paths explicitly. Compare paper/report differences without assuming misconduct or equivalence.
Deliver a claim ledger: reproduced, partly reproduced, blocked by missing artefact, or synthetic demonstration. Acceptance: every reused claim has a ledger entry; one clean-environment rerun is independently reviewed. Unresolved claims stay out of marketing and production acceptance.
## R1 — Human factors and adaptation, months 1–6; follow-up thereafter
Hypothesis: transparent skill/feedback-based sequencing improves delayed retention or reporting usefulness without increasing burden. Baseline: fixed role-relevant content. Treatment: same content pool with rule-based adaptation. Hold content quality and assessment difficulty as constant as practical.
Use a preregistered comparison with randomisation at a level that limits contamination; document whether individual or team assignment is feasible before recruitment. Primary endpoint: four-week delayed knowledge score. Secondary: reporting appropriateness/time, completion, perceived relevance, accessibility and burden. Record attrition and missing outcomes. A small 3–5-organisation pilot establishes feasibility and effect-size estimates; it is not automatically a powered causal trial. Compute a subsequent sample requirement from observed variance, clustering and a declared minimum useful effect.
Contextual bandits/RL start in offline or simulated evaluation and may proceed only after a stable baseline. No biometric emotion inference or employee personality risk scores. Treat voluntary feedback as a response, not ground truth about hidden emotional state. Evidence caution: a large field study found limited value from common phishing-training formats. [Primary study](https://www.sysnet.ucsd.edu/~voelker/pubs/phishtrain-oakland25.pdf).
## R2 — Detection, drift and graph correlation, months 2–12
Compare rules, Isolation Forest and the existing clustering/fusion approach on documented public data and later authorised shadow-mode customer observations. Split by time and, where applicable, user/site; fit transforms only on training data. Test source ablations and label quality. Graph features require a documented security purpose and cannot become employee social profiling.
Metrics: precision-recall, false alerts per investigator-day, detection delay, calibration, alert-review time and performance across sites/time periods. Report base rates. Promotion requires improvement over the operational baseline at the customer's agreed alert budget, a reviewed explanation, and a shadow-mode rollback plan. Do not replace this with an arbitrary historical 85% accuracy target.
## R3 — Evidence and explainability, months 3–12
Compare evidence tables/rule explanations, feature attribution and generated summaries. Test faithfulness by perturbing/removing evidence and checking that claims change appropriately. Evaluate analyst correctness and triage time using blinded tasks; clarity ratings alone are insufficient. Generated narratives must cite accessible evidence and distinguish observation from inference. Hidden model reasoning is not an audit source.
Promotion: unsupported material claims are detected in the review suite, evidence references resolve, and the richer explanation improves or preserves decision quality. Publish failures and limitations.
## R4 — Adversarial validation, months 7–18
Compare deterministic emulation with generated scenario selection; evaluate GANs only where they have a plausible advantage. Use isolated targets and fixed allowed techniques. Measure coverage, reproducibility, resource overhead, false findings, scope violations, cleanup success and remediation retest correctness. Freeze test definitions for comparative evaluation. Promotion requires passing scope/abort/cleanup tests and useful customer validation evidence, not a target volume of novel payloads.
## R5 — Local and federated intelligence, months 3–24
First measure rules/local models against an approved hosted baseline using public or permitted data. Include hardware, quantisation, latency, peak memory, energy/resource proxies and full failure costs. Verify offline mode with network observations rather than architecture assertions.
Federation starts only after useful local models, suitable participants and explicit permitted use exist. Compare local-only, lawful pooled reference where possible, and federated training across non-IID partitions. Test membership leakage, poisoning and update integrity. Define privacy accounting before claiming differential privacy; sharing gradients is not proof of confidentiality. Homomorphic encryption and secure aggregation remain evaluated options rather than universal requirements. [NIST discussion of federated-learning privacy attacks](https://www.nist.gov/blogs/cybersecurity-insights/privacy-attacks-federated-learning).
## R6 — Agent reliability and control, months 1–24
Begin with 20 representative internal tasks: source retrieval/citation checking, bounded repository changes, experiment execution and report drafting. Compare manual/template workflow, one agent, and later delegated workers on the same tasks and budgets. Run at least three repeats per task/configuration as an initial reliability screen; enlarge the suite before external claims.
Measure completion correctness, citation support, side-effect correctness, clean-task success, injection success, authority violations, recovery behaviour, latency and cost. Add malicious instructions to documents, repository files, tool results and memory in an isolated benchmark. Distinguish weak capability from effective enforcement. Use AgentLAB, AMA-Bench and AgentFlow as research inputs; benchmark results do not generalise automatically to customer workloads. [Evidence register](13-evidence-register.md).
## Outputs and publication
| Window | Intended artefact | Product decision informed |
|---|---|---|
| M1–3 | Reproduction ledger, baseline code/configuration and internal agent benchmark | Which legacy results and tooling to reuse |
| M4–6 | Training feasibility report and anonymised/synthetic public evaluation package | Adaptation and customer claims |
| M7–12 | Detection/explanation study and connector evaluation | Security Operations promotion |
| M13–18 | Safe-validation and local-runtime benchmark | Defense Box release |
| M19–24 | Agent enforcement/recovery evaluation; conditional federation/OT findings | Agent Security and next portfolio cycle |
Publication venue and submission timing follow completed evidence, not promised acceptance dates. Release code, schemas and permitted artefacts; document withheld data and reproducibility limits. Each production promotion needs RL evidence review, PS security/operations review and PL value/scope approval.

## Slide 31
R0: reproducibility before product claims
Trace each result
Dataset, label source, preprocessing, split, seed, code and output.
Resolve differences
Map mock-data reports and paper metrics to their exact execution paths.
Reject missing ground truth
Evaluation must fail rather than manufacture labels.
Publish the status
Reproduced, partly reproduced, blocked or synthetic demonstration.
31
Notes: R0: reproducibility before product claims
Trace each result: Dataset, label source, preprocessing, split, seed, code and output.
Resolve differences: Map mock-data reports and paper metrics to their exact execution paths.
Reject missing ground truth: Evaluation must fail rather than manufacture labels.
Publish the status: Reproduced, partly reproduced, blocked or synthetic demonstration.
Project documentation: implementation-plan/06-research-programme.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://www.sysnet.ucsd.edu/~voelker/pubs/phishtrain-oakland25.pdf
https://www.nist.gov/blogs/cybersecurity-insights/privacy-attacks-federated-learning

## Slide 32
R1: adaptive learning evaluation
Design element | Protocol
Comparison | Fixed role-relevant content versus rule-based adaptation
Primary outcome | Knowledge retention after four weeks
Secondary outcomes | Reporting behaviour, completion, relevance and burden
Pilot interpretation | Feasibility and effect estimates before a powered causal trial
A small pilot cannot establish a guaranteed reduction in phishing risk.
32
Notes: R1: adaptive learning evaluation
Comparison / Fixed role-relevant content versus rule-based adaptation
Primary outcome / Knowledge retention after four weeks
Secondary outcomes / Reporting behaviour, completion, relevance and burden
Pilot interpretation / Feasibility and effect estimates before a powered causal trial
Project documentation: implementation-plan/06-research-programme.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://www.sysnet.ucsd.edu/~voelker/pubs/phishtrain-oakland25.pdf
https://www.nist.gov/blogs/cybersecurity-insights/privacy-attacks-federated-learning

## Slide 33
R2–R3: useful detection and explanation
Detection | Explanation
Time/site separation and leakage checks | Claims cite the evidence available to the investigator
Rules versus clustering/fusion baselines | Test faithfulness by changing supporting evidence
False alerts per investigator-day | Measure decision quality and triage time
Shadow-mode promotion | Clarity ratings alone do not establish correctness
33
Notes: R2–R3: useful detection and explanation
Time/site separation and leakage checks / Claims cite the evidence available to the investigator
Rules versus clustering/fusion baselines / Test faithfulness by changing supporting evidence
False alerts per investigator-day / Measure decision quality and triage time
Shadow-mode promotion / Clarity ratings alone do not establish correctness
Project documentation: implementation-plan/06-research-programme.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://www.sysnet.ucsd.edu/~voelker/pubs/phishtrain-oakland25.pdf
https://www.nist.gov/blogs/cybersecurity-insights/privacy-attacks-federated-learning

## Slide 34
R4–R5: validation and privacy research
Adversarial validation
Compare reproducible scripted checks before generative methods or GANs.
Local inference
Measure quality, latency, memory and failure cost on actual hardware.
Federated intelligence
Require useful local models, permitted data use and a privacy threat model.
Industrial research
Use passive lab evidence before a scoped customer pilot.
34
Notes: R4–R5: validation and privacy research
Adversarial validation: Compare reproducible scripted checks before generative methods or GANs.
Local inference: Measure quality, latency, memory and failure cost on actual hardware.
Federated intelligence: Require useful local models, permitted data use and a privacy threat model.
Industrial research: Use passive lab evidence before a scoped customer pilot.
Project documentation: implementation-plan/06-research-programme.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://www.sysnet.ucsd.edu/~voelker/pubs/phishtrain-oakland25.pdf
https://www.nist.gov/blogs/cybersecurity-insights/privacy-attacks-federated-learning

## Slide 35
Frontier agent research
Research input | AegisAI experiment
AgentLAB, February 2026 | Long-horizon attacks through retrieved content and tools
AMA-Bench, February 2026 | Explicit task state and retrieval versus richer memory
AgentFlow, August 2026 | Independent policy and data-flow enforcement
Repeated task evaluation | Success, authority violations, recovery and total cost
Research findings remain bounded by their benchmarks. They do not certify product safety.
35
Notes: Frontier agent research
AgentLAB, February 2026 / Long-horizon attacks through retrieved content and tools
AMA-Bench, February 2026 / Explicit task state and retrieval versus richer memory
AgentFlow, August 2026 / Independent policy and data-flow enforcement
Repeated task evaluation / Success, authority violations, recovery and total cost
Project documentation: implementation-plan/13-evidence-register.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://docs.netbird.io/about-netbird/how-netbird-works
https://docs.netbird.io/manage/networks/how-routing-peers-work
https://docs.netbird.io/selfhosted/enterprise
https://github.com/netbirdio/netbird/blob/main/LICENSE
https://netbird.io/pricing
https://docs.netbird.io/agent-network
https://docs.netbird.io/agent-network/how-it-works
https://docs.netbird.io/agent-network/quickstart
https://tailscale.com/pricing
https://www.firezone.dev/pricing
https://wazuh.com/cloud/
https://netbird.io/knowledge-hub/control-center-draft-mode
https://netbird.io/knowledge-hub/norsk-helsenett
https://netbird.io/knowledge-hub/security-advisory-daemon-ipc-local-privilege-escalation
https://tailscale.com/blog/aperture-public-beta
https://www.knowbe4.com/press/knowbe4-launches-aida-orchestration-as-the-first-fully-autonomous-agent-for-human-risk-management
https://wazuh.com/resources/case-studies/digifors-mssp-services/
https://digital-strategy.ec.europa.eu/en/policies/cra-reporting
https://www.sysnet.ucsd.edu/~voelker/pubs/phishtrain-oakland25.pdf
https://arxiv.org/abs/2602.16901
https://arxiv.org/abs/2602.22769
https://arxiv.org/abs/2608.22868
https://www.anthropic.com/engineering/demystifying-evals-for-ai-agents
https://www.anthropic.com/engineering/building-c-compiler
https://www.nist.gov/blogs/cybersecurity-insights/privacy-attacks-federated-learning
https://docs.openhands.dev/sdk/arch/security
https://cyclonedx.org/specification/overview/
https://osv.dev/
https://github.com/apache/caldera
https://attack.mitre.org/tactics/ics/
https://attack.mitre.org/mitigations/ics/
https://www.enisa.europa.eu/publications/nis-investments-2025
https://www.enisa.europa.eu/news/nis360-the-bigger-picture-on-maturity-and-criticality-of-nis-critical-sectors
https://dyn.cncs.gov.pt/pt/detalhe/art/135998/novo-regime-juridico-da-ciberseguranca-entra-em-vigor
https://eur-lex.europa.eu/eli/reg/2016/679/oj/
https://eur-lex.europa.eu/eli/reg/2024/1689/oj
https://digital-strategy.ec.europa.eu/en/policies/regulatory-framework-ai
https://digital-strategy.ec.europa.eu/en/policies/cra-summary
https://www.nccoe.nist.gov/projects/cyber-ai-profile
https://www.nccoe.nist.gov/publications/csf-profile/nist-ir-8596-ipd-cybersecurity-framework-profile-artificial-intelligence

## Slide 36
Internal agent workspace
Early scope
Literature review, citation checking, bounded code work and experiments.
Runtime baseline
Evaluate OpenHands with one bounded worker and controlled model/tool interfaces.
Data and authority
Separate curated knowledge, task history and untrusted text. Keep secrets outside workers.
Promotion
Commercial Agent Security follows measured internal results and separate customer discovery.
36
Notes: Internal agent workspace
Early scope: Literature review, citation checking, bounded code work and experiments.
Runtime baseline: Evaluate OpenHands with one bounded worker and controlled model/tool interfaces.
Data and authority: Separate curated knowledge, task history and untrusted text. Keep secrets outside workers.
Promotion: Commercial Agent Security follows measured internal results and separate customer discovery.
Project documentation: implementation-plan/07-internal-agent-workspace.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://docs.openhands.dev/sdk/arch/security
DETAILED PROJECT REFERENCE
# Internal research and engineering workspace
[Index](README.md) · Owner: Research Lead with Platform/Security Lead
## Purpose and limited early scope
Support literature review, citation verification, bounded code changes, experiment execution and technical writing. This is an internal productivity capability in months 1–3, not a competing commercial release or an attempt to implement every component in the supplied frontier-agent notes.
Begin with OpenHands as the engineering-runtime candidate, one bounded worker per task, an approved model adapter and a controlled tool gateway. Use the runtime's security features as integration aids; deterministic permissions and sandbox boundaries remain independent. [OpenHands security architecture](https://docs.openhands.dev/sdk/arch/security).
## Minimal workflow
1. A researcher defines a task, permitted sources/files, budget and expected artefact.
2. Retrieval saves source URL, author/publisher, date, access date, document version and supporting passage location.
3. The worker proposes a bounded action. The gateway validates scope and any required approval.
4. A dedicated worker VM executes an unprivileged task container with a task workspace and no host socket or production secrets.
5. Checkpoints persist task state and evidence, not unrestricted model-generated instructions.
6. A reviewer checks citations, code diff or experiment output before promotion or publication.
Maintain a reference library and machine-readable bibliography alongside experiment manifests. GROBID/Pandoc or equivalent tools may be added when input/output needs justify them; a custom research browser and custom IDE are not initial deliverables.
## Model and memory decisions
Evaluate one local open-weight model supported by available hardware against one approved hosted model using R6 tasks. Gemma and other families named in the notes are candidates, not locked model/version/hardware requirements. Verify licence and actual resource use at selection. Sensitive data cannot be silently routed to the hosted option on local failure.
Start with explicit task state, artefact storage and PostgreSQL-backed retrieval. Separate curated knowledge, task history and untrusted retrieved text. Every memory item has source, scope, timestamp, retention and deletion support. Do not introduce a graph database, shared autonomous memory or fine-tuning before showing a baseline deficiency.
Tools begin with read-only retrieval, workspace file access and isolated tests. Network destinations are allowlisted. Shell operations, browser actions and external writes have separate capabilities. Limit run time, calls, concurrency and spend; do not rely on a natural-language instruction as the limit.
## Adoption schedule
| Window | Deliverable | Acceptance |
|---|---|---|
| M1 | Fixed task suite, model/tool policy and disposable sandbox | No production credentials; cost and action logs available |
| M2 | Retrieval/citation and experiment workflows | Human review finds traceable sources; restart does not duplicate external actions |
| M3 | Measured internal comparison | Correctness/cost report and decision to retain, simplify or replace components |
| M4–12 | Incremental use and adversarial tests | Measurable benefit within research allocation; isolation preserved |
| M13–18 | Extract reusable identity/gateway/execution contracts | Independent of runtime-specific objects; external discovery started |
| M19–24 | Productise validated capabilities | Agent Security release gates, not internal-use status alone |
## Supplied-note decisions
Retain model routing, tool contracts, scientific provenance, durable state and explicit authority from all four research notes. Defer full multi-agent swarms, RL training infrastructure, many databases, Kafka/Ray/Kubernetes and unrestricted computer use. Introduce Temporal only when workflow durability requirements exceed the simpler job/checkpoint design. Trial NetBird Agent Network separately as described in the [NetBird study](04-netbird-study.md).
Internal acceptance includes injected-source tests, blocked secret export, denied network targets, read-only replay, cancellation, corrupted checkpoint recovery and an audit record of every authorised side effect. Frontier research informs these evaluations; it does not confer production maturity.

## Slide 37
Roadmap: months 1–12
Window | Primary delivery | Gate
M1–3 | Human Firewall pilot and shared foundations | G1
M4–6 | Paid training pilots and production release | G2
M7–9 | Security Operations pilot | G3
M10–12 | Supported Security Operations release | G4
Research runs within its allocation. Each product works independently.
37
Notes: Roadmap: months 1–12
M1–3 / Human Firewall pilot and shared foundations / G1
M4–6 / Paid training pilots and production release / G2
M7–9 / Security Operations pilot / G3
M10–12 / Supported Security Operations release / G4
Project documentation: implementation-plan/08-roadmap-backlog.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
DETAILED PROJECT REFERENCE
# Roadmap, dependencies and first 90 days
[Index](README.md) · Owner: Product Lead · Kickoff: not yet assigned
All months are relative to recorded kickoff. Gates are targets, not evidence of completion. The first training release is constrained to months 3–6; continuing maintenance does not extend its primary development window. Gate definitions are in the [production handbook](12-production-handbook.md).
## 24-month delivery sequence
| Window | Primary stream / gate | Research and preparation | Dependency / accountable role |
|---|---|---|---|
| M1–3 | Human Firewall pilot, G1 | R0; R1 protocol; internal workspace; operations interviews | Foundation controls; PL |
| M4–6 | Human Firewall production, G2 | R1 field feasibility; operations connector samples | G1 and customer/support evidence; PL |
| M7–9 | Security Operations pilot, G3 | R2/R3; passive appliance lab | G2 stable operation and own standalone product identity; PS |
| M10–12 | Security Operations production, G4 | R4 harness; local-model comparison | G3 ingestion/finding utility; PS |
| M13–15 | Defense Box pilot, G5 | R4/R5; agent customer discovery | G4 evidence/adapters; PS |
| M16–18 | Defense Box production, G6 | Conditional federation and passive OT lab | G5 scope, abort, cleanup and supportability; PS |
| M19–21 | Agent Security pilot, G7 | R6 long-horizon attacks and recovery | Internal tooling evidence and distinct external need; PS |
| M22–24 | Agent Security production, G8 | Conditional OT pilot, insurer/MSP and Lusophone discovery | G7 and portfolio operating capacity; PL/PS |
Each subsequent stream requires sufficient stability/capacity, not purchase of the previous product by its customers. A failed gate moves dependent work or reduces breadth. Research can continue within its allocation without silently opening a second production programme.
## Foundation backlog
| ID | Deliverable | Owner | Dependency | Done evidence |
|---|---|---|---|---|
| CORE-01 | Organisation isolation, OIDC and role enforcement | PS | Data/role design | Cross-organisation and revoked-user denial tests |
| CORE-02 | Event/evidence contracts, schema validation and data lifecycle | PS/RL | Classification review | Valid/invalid fixtures, provenance, deletion and dedup tests |
| CORE-03 | Reproducible deploy, secrets, CI and dependency inventory | PS | Supported stack choice | Clean staging deployment with pinned images and secret scans |
| CORE-04 | Audit, persisted jobs and action approvals | PS | CORE-01/02 | Approval replay denial; restart/uncertain-side-effect reconciliation |
| CORE-05 | Monitoring, backup, restore and rollback | PS | CORE-03 | Timed restore; failing-release rollback and alert exercise |
| CORE-06 | Optional NetBird lab and provider adapter design | PS | CORE-01; isolated lab | Connectivity test matrix; licence/component record |
| DISC-01 | Ten customer interviews and product/pricing synthesis | PL | Interview guide | Documented needs, alternatives, buyer authority and objections |
| RES-01 | Legacy claim ledger and one independent rerun | RL | Source/data inventory | R0 report with reproduced/blocked distinctions |
| AG-01 | Internal agent workflow baseline | RL/PS | Sandbox and tool policy | R6 benchmark, cost and violation report |
## First 90 days: ordered sprint plan
| Period | Tasks and output | Acceptance / review |
|---|---|---|
| Weeks 1–2 | Assign role owners; record kickoff; DISC-01 starts; HF-01; CORE-01/02 design; RES-01 inventory | Requirements, data-purpose matrix, three scenarios, source traceability and threat model reviewed |
| Weeks 3–4 | CORE-01/03; HF-02/03 vertical slice; CORE-06 bounded lab; first R0 rerun | Administrator assigns a versioned scenario; learner completes it in isolated staging |
| Weeks 5–6 | HF-04/05; CORE-02/04; AG-01 baseline | Explained recommendation, authorised report, audit and durable event ingestion |
| Weeks 7–8 | HF-06; CORE-05; R1 protocol; finish DISC-01 | Twelve reviewed scenarios; monitoring; pilot criteria and research endpoints fixed |
| Weeks 9–10 | Restore/rollback, accessibility, rights/export/deletion; cost model; HF-07 starts | Timed exercises and defects triaged; draft pilot agreement and measured support assumptions |
| Weeks 11–13 | Independent pilot release review; onboarding rehearsal; operations samples/specification | G1 evidence signed, unresolved risks disclosed, next sprint backlog limited to G2 priorities |
These are sequencing buckets, not an assertion that every item fits regardless of staffing. During planning, split tasks into reviewable issues of a few days each and preserve parent IDs. PS owns security-sensitive sequencing; research work cannot delay basic training journeys except for a genuine safety/data blocker.
## Capacity and commercial checkpoints
Three-FTE baseline: 1.8 product, 0.6 research/discovery, 0.6 support/operations. Review actual hours every sprint. A fourth contributor first reduces integration/reliability risk. At two contributors postpone optional connectors, generated content and custom integrations; do not remove isolation or recovery work.
At M3 assess recruitment and willingness to pay; M6 assess training support economics and renewal signals; M12 assess operations alert workload and partner demand; M18 assess appliance deployment/support cost; M24 assess agent-policy value and portfolio sustainability. The target of 3–5 paid training pilots is unconfirmed until contracts exist. Customer count alone does not justify expansion.
## Tracking and change control
Issue fields: ID, product/WP, owner, dependency, estimate, acceptance evidence, security/data impact, status, blocked reason. Initial state for all implementation tasks is **not started / not verified by this documentation exercise**. Gates can be pending, passed with evidence, or failed. Scope changes require a decision-register entry and updates to the affected product, contract, research protocol and release gate.

## Slide 38
Roadmap: months 13–24
Window | Primary delivery | Gate
M13–15 | Defense Box and Validation pilot | G5
M16–18 | Supported appliance release | G6
M19–21 | Agent Security external pilot | G7
M22–24 | Agent Security release and portfolio integration | G8
OT, federation and partnerships remain conditional on evidence and capacity.
38
Notes: Roadmap: months 13–24
M13–15 / Defense Box and Validation pilot / G5
M16–18 / Supported appliance release / G6
M19–21 / Agent Security external pilot / G7
M22–24 / Agent Security release and portfolio integration / G8
Project documentation: implementation-plan/08-roadmap-backlog.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.

## Slide 39
First 90 days
Period | Delivery focus
Weeks 1–2 | Owners, discovery, content, contracts and threat model
Weeks 3–4 | Identity, deployment and a complete training slice
Weeks 5–8 | Adaptation, reports, audit, monitoring and pilot programme
Weeks 9–10 | Recovery, privacy, accessibility and cost model
Weeks 11–13 | Pilot release review and Operations preparation
39
Notes: First 90 days
Weeks 1–2 / Owners, discovery, content, contracts and threat model
Weeks 3–4 / Identity, deployment and a complete training slice
Weeks 5–8 / Adaptation, reports, audit, monitoring and pilot programme
Weeks 9–10 / Recovery, privacy, accessibility and cost model
Weeks 11–13 / Pilot release review and Operations preparation
Project documentation: implementation-plan/08-roadmap-backlog.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.

## Slide 40
Shared implementation dependencies
Foundation task | Product dependency
CORE-01 / CORE-02 | Identity, isolation, schemas and evidence before customer data
CORE-03 / CORE-05 | Repeatable deployment, monitoring and recovery before release
CORE-04 | Audit and bound approvals before consequential actions
CORE-06 / AG-01 | Optional connectivity and internal agent experiments stay bounded
40
Notes: Shared implementation dependencies
CORE-01 / CORE-02 / Identity, isolation, schemas and evidence before customer data
CORE-03 / CORE-05 / Repeatable deployment, monitoring and recovery before release
CORE-04 / Audit and bound approvals before consequential actions
CORE-06 / AG-01 / Optional connectivity and internal agent experiments stay bounded
Project documentation: implementation-plan/08-roadmap-backlog.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.

## Slide 41
Team capacity and responsibilities
Role / allocation | Responsibility
Product Lead | Customers, scope, packaging and portfolio decisions
Platform/Security Lead | Architecture, operations and technical release approval
Application Engineer | Product journeys, UI and supported integrations
Research Lead | Methods, experiments and scientific claims
Three-FTE planning baseline: 60% product, 20% research/discovery, 20% support. People may hold multiple roles.
41
Notes: Team capacity and responsibilities
Product Lead / Customers, scope, packaging and portfolio decisions
Platform/Security Lead / Architecture, operations and technical release approval
Application Engineer / Product journeys, UI and supported integrations
Research Lead / Methods, experiments and scientific claims
Project documentation: implementation-plan/01-portfolio-strategy.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.

## Slide 42
Work packages 1–5
Work package | Owner | Deliverable
WP1 AI experiments | Research | Protocols and promotion evidence
WP2 Data model | Platform / Research | Schemas, provenance and boundaries
WP3 Gamification / UX | Application | Training release and design system
WP4 Edge infrastructure | Platform | Collectors, local AI and appliance
WP5 Governance | Product / Security | Applicability and oversight records
42
Notes: Work packages 1–5
WP1 AI experiments / Research / Protocols and promotion evidence
WP2 Data model / Platform / Research / Schemas, provenance and boundaries
WP3 Gamification / UX / Application / Training release and design system
WP4 Edge infrastructure / Platform / Collectors, local AI and appliance
WP5 Governance / Product / Security / Applicability and oversight records
Project documentation: implementation-plan/09-work-packages.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
DETAILED PROJECT REFERENCE
# Work-package ownership and deliverables
[Index](README.md) · Owner: Product Lead
Owner roles: PL = Product Lead; PS = Platform/Security Lead; AE = Application Engineer; RL = Research Lead. Assign people at kickoff. Work packages are responsibilities across one product stream, not ten simultaneous teams.
| WP | Owner | Deliverables | Dependencies | Acceptance and milestones |
|---|---|---|---|---|
| WP1 AI experiments and modelling | RL | R0 ledger; R1–R6 protocols; dataset/model cards; evaluation artefacts; promotion reports | WP2/7 data rights and quality | Reproducible inputs/outputs and baseline comparison; each relevant gate |
| WP2 Data model and Human Boundary Ecosystem | PS/RL | Data dictionary; classification; event/evidence/identity contracts; learning/security separation | WP5 purpose and threat model | Schema fixtures, tenant reference checks and provenance; CORE-02 before G1 |
| WP3 Gamification and UX | AE | Learner/admin journeys; content taxonomy; Portuguese scenarios; accessible design system; later product usability | WP1 baseline, WP2 outcomes | Principal journeys and reviewed content; G1/G2, then capped maintenance |
| WP4 Edge and privacy infrastructure | PS | Collector identity; local buffering/inference; connectivity adapter; appliance packaging; federation lab | WP2/5/7; CORE-03 | Offline/loss/rotation/upgrade tests; G3–G6; federation conditional |
| WP5 Regulatory and governance alignment | PL with PS | Applicability records; threat model; customer terms/DPA input; AI oversight; authorised-test scope | Product intended use and WP7 inventory | Qualified review for relevant obligations; gate-specific sign-off and limitations |
| WP6 SME operational integration | PL/AE | Discovery; onboarding; supported connectors; customer workflows; training/reporting cycles; offboarding | WP3/4/8/9 | Customer walkthrough, connector conformance and support documentation; all gates |
| WP7 Data lifecycle and rights | PS | Catalogue; metadata/lineage; quality checks; retention/deletion; rights workflow; research export controls | WP2 schemas and WP5 purpose | Export/delete/restore-time deletion tests and quality dashboard; before G1, extended each product |
| WP8 Product and commercialisation | PL | Product requirements; packaging; price/cost hypotheses; pilot agreements; community boundary; partner strategy | Customer evidence and WP5/9 costs | Buyer validation, support economics and coherent offer; quarterly checkpoints |
| WP9 Platform engineering and reliability | PS | Identity; CI/CD; IaC; secrets; observability; jobs; backups; upgrade/rollback; dependency inventory | WP2/5; implementation backlog | CORE-01–05 evidence and runbooks; before first customer release |
| WP10 Validation and release assurance | PS; independent reviewer | Test matrix; adversarial checks; security assessment; release manifest; gate record | Product and WP1/5/9 evidence | No unresolved critical/high security findings at GA; operational and product acceptance demonstrated |
## Cross-package handoffs
WP1 supplies a research candidate plus limitations, never an implicit production approval. WP2/7 supply permitted data and provenance. WP4/9 package the candidate behind a reversible feature flag. WP10 validates representative behaviour and failure handling. WP8 confirms a customer reason to support it. PS and PL jointly accept production promotion; RL approves scientific claims.
## Minimum recurring cadence
Two-week product review: completed evidence, defects, support load and next bounded sprint. Monthly research/commercial review: hypotheses, negative results, spend, discovery and product implications. Release review: WP10 gate record signed by the accountable owner and second reviewer. Quarterly portfolio review: sequencing, capacity and deferred initiatives, including federation/OT/insurance/international scope.
## Deliverable conventions
Each deliverable records version, owner, status, supporting artefact links and review date. A research report can be complete with a negative result. A production gate cannot pass on a roadmap statement, vendor benchmark or unexecuted test plan. Source changes are tracked in [traceability](02-source-traceability.md); implementation decisions in the [decision register](14-decisions.md).

## Slide 43
Work packages 6–10
Work package | Owner | Deliverable
WP6 SME integration | Product / Application | Onboarding and connectors
WP7 Data lifecycle | Platform | Quality, retention and rights
WP8 Commercialisation | Product | Packaging and pilot economics
WP9 Reliability | Platform | CI/CD, recovery and operations
WP10 Release assurance | Security / reviewer | Tests, assessment and gate record
43
Notes: Work packages 6–10
WP6 SME integration / Product / Application / Onboarding and connectors
WP7 Data lifecycle / Platform / Quality, retention and rights
WP8 Commercialisation / Product / Packaging and pilot economics
WP9 Reliability / Platform / CI/CD, recovery and operations
WP10 Release assurance / Security / reviewer / Tests, assessment and gate record
Project documentation: implementation-plan/09-work-packages.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.

## Slide 44
Market validation
Initial discovery
Ten interviews with buyers and operators across target Portuguese SMEs.
Pilot objective
Recruit 3–5 paid training pilots after technical and privacy readiness.
Later products
Interview at least five relevant buyers/operators before each new product.
Commercial checkpoints
Assess renewal, support effort, cost and willingness to pay before expansion.
44
Notes: Market validation
Initial discovery: Ten interviews with buyers and operators across target Portuguese SMEs.
Pilot objective: Recruit 3–5 paid training pilots after technical and privacy readiness.
Later products: Interview at least five relevant buyers/operators before each new product.
Commercial checkpoints: Assess renewal, support effort, cost and willingness to pay before expansion.
Project documentation: implementation-plan/10-market-business-model.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://www.enisa.europa.eu/publications/nis-investments-2025
https://netbird.io/pricing
https://tailscale.com/pricing
https://www.firezone.dev/pricing
https://wazuh.com/cloud/
https://www.knowbe4.com/press/knowbe4-launches-aida-orchestration-as-the-first-fully-autonomous-agent-for-human-risk-management
https://tailscale.com/blog/aperture-public-beta
https://netbird.io/knowledge-hub/norsk-helsenett
https://wazuh.com/resources/case-studies/digifors-mssp-services/
DETAILED PROJECT REFERENCE
# Market, packaging and open-core business model
[Index](README.md) · Owner: Product Lead · Evidence snapshot: 18 September 2026
## Market thesis and limits
Hypothesis: Portuguese SMEs will pay for supported, understandable security workflows that reduce administration and make evidence usable. Validate this with buyers, not broad cyber-loss statistics. ENISA's NIS Investments 2025 survey covers 1,080 organisations and is 83% large enterprises; its budget figures cannot be treated as a representative Portuguese SME spending baseline. [ENISA report](https://www.enisa.europa.eu/publications/nis-investments-2025).
Start discovery with 20–200-person professional-services and technology-enabled businesses, then IT service providers. Interview the actual budget holder and operator. Later appliances need customers with accessible local infrastructure; Agent Security needs a separate engineering/security buyer. Do not assume the training buyer will buy all subsequent products.
## Competitive references
Prices are page observations, not quotes, converted currencies, or an AegisAI price recommendation. Recheck billing basis, taxes, region and scope before comparison.
| Reference | Observed model and positioning | Lesson / competitive implication |
|---|---|---|
| [NetBird](https://netbird.io/pricing) | Cloud Free up to 5 users; Team EUR 6 and Business EUR 12 per active user/month on the accessed page; enterprise custom; self-hosted terms separate | Free adoption can coexist with paid operation, support and organisational capabilities |
| [Tailscale](https://tailscale.com/pricing) | Personal entry tier; Standard/Premium and enterprise tiers; current pricing separates organisational usage from free personal use | Free is not synonymous with open-source server availability; agent governance is an adjacent competitive area |
| [Firezone](https://www.firezone.dev/pricing) | Free, Team and Enterprise access offerings | Clear tier boundaries and enterprise support are alternatives to charging for every core capability |
| [Wazuh Cloud](https://wazuh.com/cloud/) | Managed deployment of an open-source security platform | Integration, reliability and operations can support revenue around an open foundation |
| [KnowBe4 AIDA](https://www.knowbe4.com/press/knowbe4-launches-aida-orchestration-as-the-first-fully-autonomous-agent-for-human-risk-management) | Vendor announced autonomous training orchestration in February 2026 | Adaptive/AI training alone is not distinctive; prove local fit, privacy and customer outcomes |
For Security Operations, compare the customer's existing Wazuh/SIEM/endpoint workflows against AegisAI's evidence-to-remediation experience. For Defense Box, compare managed sensors and existing validation tools; do not sell an upstream scanner with only a new logo. For Agent Security, compare network/provider governance with task-level tool authority and safe execution. [Tailscale Aperture announcement](https://tailscale.com/blog/aperture-public-beta).
## Vendor use cases and what they establish
- NetBird's August 2026 Norsk Helsenett case describes identity-aware access and simpler administration in healthcare IT. It supports investigation of enrolment/support needs; it does not demonstrate AegisAI suitability for regulated healthcare. [Case](https://netbird.io/knowledge-hub/norsk-helsenett).
- Wazuh's DigiFors case illustrates an MSSP combining an open platform with maintained customer services. It motivates a later partner model; its reported outcomes are vendor/customer claims, not audited AegisAI unit economics. [Case](https://wazuh.com/resources/case-studies/digifors-mssp-services/).
## Product packaging
| Package | Included value | Cost/billing driver | Separate commercial work |
|---|---|---|---|
| Human Firewall | Managed training, reviewed content, reporting, business-hours support | Organisation base + active learner band | Bespoke content and integrations |
| Security Operations | Supported ingestion, asset/SCA findings, investigations and guided playbooks | Organisation base + asset/event-volume band | Additional sources, long retention, advanced response integration |
| Defense Box | Supported software appliance, updates, diagnostics and scoped validation | Site/appliance + supported validation allowance | Installation, hardware, industrial assessment |
| Agent Security | Workload policy, gateway, audit and execution controls | Organisation/workload tier + measured execution usage | Private deployment, enterprise connectors, dedicated support |
Bundle discounts must not obscure per-product costs. Publish inclusions, usage limits, overage handling and support hours. No unlimited telemetry, agent compute or bespoke support by default. No product is priced or sold in this documentation exercise.
## Cost model and illustrative sensitivity
Monthly direct service cost per customer:
`C = compute + database/storage/backup + network/relay egress + upstream licences + model usage + support hours × loaded hourly cost + monitoring/security allocation`
At desired gross margin `g`, the minimum recurring price before sales/R&D overhead is `P = C / (1 - g)`. Onboarding is priced separately from recurring operations. Include engineering, sales, tax and working-capital costs in company planning; gross margin is not profit.
Illustration only: EUR 60 infrastructure + EUR 15 backup/monitoring + EUR 10 model use + 2 support hours at EUR 40 = EUR 165 direct monthly cost, excluding any paid upstream licence. At a hypothetical 60% gross margin the price floor is EUR 412.50. Four support hours make cost EUR 245 and the same floor EUR 612.50. These are invented scenario inputs to expose support sensitivity, not measured costs or a proposed market price.
Discovery must test whether customers value an offer above its measured cost floor. If not, reduce onboarding/support friction, change the segment or stop expansion; do not infer profitability from free upstream software. Track paid conversion, renewal, support hours, gross margin, acquisition effort and cash collection separately.
## Open-source and enterprise boundary
Default licence proposal for original community code: Apache-2.0, after contributor/IP and upstream compatibility review. This document does not license existing source or override dependencies. Keep a useful community core: schemas, selected collectors/adapters, basic workflows, evaluation harnesses and permitted research artefacts. Community users retain export and self-hosting paths.
Paid value: managed EU operation, fleet administration, enterprise integrations, maintained deployment options, support agreements and scoped implementation. Proprietary extensions, if adopted, have documented API boundaries and separate terms; legal review decides compatibility. Do not hold fixes for shared security flaws behind a paid gate. Establish SECURITY.md, contribution guidance, release policy, issue triage and maintenance ownership before public launch.
Custom-client work requires a statement of work, acceptance, recurring maintenance price, IP boundary and a reuse decision. Prefer configuration or maintained adapters; decline divergent customer forks without funded support. NetBird commercial resale/hosting permissions and pricing remain external validations, not assumed rights.
## Discovery protocol and expansion gates
Ten initial interviews: current workflow, recent incident/administration pain, incumbent tools, buying authority, budget process, data constraints, procurement, support expectations and willingness to pilot. Record alternatives and disconfirming evidence. Target 3–5 paid training pilots after readiness; no customers are claimed to exist.
Before each later product, interview at least five relevant buyers/operators and obtain scoped pilot interest. Expand through MSPs after repeatable direct onboarding. Insurance evidence exchange and Lusophone expansion remain M22–24 discovery: confirm buyer, data permissions, distribution partner and economics before adding delivery commitments. No numerical TAM or revenue forecast is justified by the reviewed evidence; build a bottom-up segment model only from sourced firm counts and measured conversion assumptions.

## Slide 45
Competitive references
Reference | What the team should learn
NetBird / Tailscale / Firezone | Adoption tiers, managed access and organisational controls
Wazuh | Supported services around an open security platform
KnowBe4 AIDA | AI training orchestration already has strong competitors
Agent-access offerings | Validate task-level authority and execution differentiation
Vendor claims and case studies inform discovery. They do not validate AegisAI results.
45
Notes: Competitive references
NetBird / Tailscale / Firezone / Adoption tiers, managed access and organisational controls
Wazuh / Supported services around an open security platform
KnowBe4 AIDA / AI training orchestration already has strong competitors
Agent-access offerings / Validate task-level authority and execution differentiation
Project documentation: implementation-plan/10-market-business-model.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://www.enisa.europa.eu/publications/nis-investments-2025
https://netbird.io/pricing
https://tailscale.com/pricing
https://www.firezone.dev/pricing
https://wazuh.com/cloud/
https://www.knowbe4.com/press/knowbe4-launches-aida-orchestration-as-the-first-fully-autonomous-agent-for-human-risk-management
https://tailscale.com/blog/aperture-public-beta
https://netbird.io/knowledge-hub/norsk-helsenett
https://wazuh.com/resources/case-studies/digifors-mssp-services/

## Slide 46
Open core and commercial value
Useful community foundation | Paid operating value
Schemas and selected adapters | Managed EU operation and enterprise administration
Basic workflows and export | Maintained integrations and supported deployment
Evaluation tools and research artefacts | Support agreements and implementation services
Documented self-hosting path | Customer-specific work with explicit maintenance scope
Apache-2.0 is the default proposal for original components, subject to IP and upstream review.
46
Notes: Open core and commercial value
Schemas and selected adapters / Managed EU operation and enterprise administration
Basic workflows and export / Maintained integrations and supported deployment
Evaluation tools and research artefacts / Support agreements and implementation services
Documented self-hosting path / Customer-specific work with explicit maintenance scope
Project documentation: implementation-plan/10-market-business-model.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://www.enisa.europa.eu/publications/nis-investments-2025
https://netbird.io/pricing
https://tailscale.com/pricing
https://www.firezone.dev/pricing
https://wazuh.com/cloud/
https://www.knowbe4.com/press/knowbe4-launches-aida-orchestration-as-the-first-fully-autonomous-agent-for-human-risk-management
https://tailscale.com/blog/aperture-public-beta
https://netbird.io/knowledge-hub/norsk-helsenett
https://wazuh.com/resources/case-studies/digifors-mssp-services/

## Slide 47
Product packaging
Product | Primary cost and billing driver
Human Firewall | Organisation base and active learner band
Security Operations | Organisation base, assets and event volume
Defense Box | Site/appliance and supported validation allowance
Agent Security | Organisation/workloads and execution usage
Onboarding and bespoke integrations have separate scopes. No prices or contracts are approved yet.
47
Notes: Product packaging
Human Firewall / Organisation base and active learner band
Security Operations / Organisation base, assets and event volume
Defense Box / Site/appliance and supported validation allowance
Agent Security / Organisation/workloads and execution usage
Project documentation: implementation-plan/10-market-business-model.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://www.enisa.europa.eu/publications/nis-investments-2025
https://netbird.io/pricing
https://tailscale.com/pricing
https://www.firezone.dev/pricing
https://wazuh.com/cloud/
https://www.knowbe4.com/press/knowbe4-launches-aida-orchestration-as-the-first-fully-autonomous-agent-for-human-risk-management
https://tailscale.com/blog/aperture-public-beta
https://netbird.io/knowledge-hub/norsk-helsenett
https://wazuh.com/resources/case-studies/digifors-mssp-services/

## Slide 48
Support effort changes the price floor
Illustrative monthly scenario | 2 support hours | 4 support hours
Infrastructure, backup and model use | EUR 85 | EUR 85
Support at EUR 40 per hour | EUR 80 | EUR 160
Direct monthly cost | EUR 165 | EUR 245
Price at a hypothetical 60% margin | EUR 412.50 | EUR 612.50
Illustration only. Excludes upstream licences, sales, R&D, tax and company overhead.
48
Notes: Support effort changes the price floor
Infrastructure, backup and model use / EUR 85 / EUR 85
Support at EUR 40 per hour / EUR 80 / EUR 160
Direct monthly cost / EUR 165 / EUR 245
Price at a hypothetical 60% margin / EUR 412.50 / EUR 612.50
Project documentation: implementation-plan/10-market-business-model.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://www.enisa.europa.eu/publications/nis-investments-2025
https://netbird.io/pricing
https://tailscale.com/pricing
https://www.firezone.dev/pricing
https://wazuh.com/cloud/
https://www.knowbe4.com/press/knowbe4-launches-aida-orchestration-as-the-first-fully-autonomous-agent-for-human-risk-management
https://tailscale.com/blog/aperture-public-beta
https://netbird.io/knowledge-hub/norsk-helsenett
https://wazuh.com/resources/case-studies/digifors-mssp-services/

## Slide 49
Security and privacy risks
Risk | Required control
Cross-customer access | Isolated stacks and object-level authorisation
Agent or collector compromise | Scoped identities, revocation and execution isolation
Repeated or destructive action | Bound approvals and reconciliation
Employee surveillance | Separate purposes and restricted learning data
Unsafe validation | Explicit scope, limits, abort and cleanup
49
Notes: Security and privacy risks
Cross-customer access / Isolated stacks and object-level authorisation
Agent or collector compromise / Scoped identities, revocation and execution isolation
Repeated or destructive action / Bound approvals and reconciliation
Employee surveillance / Separate purposes and restricted learning data
Unsafe validation / Explicit scope, limits, abort and cleanup
Project documentation: implementation-plan/11-security-privacy-regulation.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://eur-lex.europa.eu/eli/reg/2016/679/oj/
https://eur-lex.europa.eu/eli/reg/2024/1689/oj
https://digital-strategy.ec.europa.eu/en/policies/regulatory-framework-ai
https://digital-strategy.ec.europa.eu/en/policies/cra-summary
https://www.nccoe.nist.gov/projects/cyber-ai-profile
https://digital-strategy.ec.europa.eu/en/policies/cra-reporting
https://dyn.cncs.gov.pt/pt/detalhe/art/135998/novo-regime-juridico-da-ciberseguranca-entra-em-vigor
DETAILED PROJECT REFERENCE
# Security, privacy and regulatory applicability
[Index](README.md) · Owner: Platform/Security Lead with Product Lead · Design controls, not a compliance certification
## Threat model and controls
| Threat | Required control | Verification |
|---|---|---|
| Cross-customer access | Separate stacks/credentials plus application object checks | Cross-organisation API/evidence/export tests |
| Compromised collector | Revocable workload identity, minimum routes, bounded configuration | Credential theft/revocation exercise |
| Prompt injection or poisoned memory | Untrusted-data separation, deterministic tool policy, isolated runtime | R6 adversarial suite and denied-action audit |
| Destructive or repeated automation | Parameter-bound approval, precondition checks, idempotency/reconciliation | Lost-response, retry and expired-approval tests |
| Software supply-chain compromise | Pinned dependencies, SBOM, scanning, signed release provenance, update policy | Build inventory and tampered-update rejection |
| Employee surveillance/purpose expansion | Separate learning/security stores and purposes; access restrictions | Data-flow/role review and privacy tests |
| Unsafe active validation | Exact scope, isolated runner, expiry, abort and cleanup | Out-of-scope and disconnect tests |
| Telemetry/log data leakage | Local minimisation, redaction, limited retention, secret isolation | Payload/log inspection and deletion exercise |
| Operating outage or stale policy | Health/freshness indicators, backup/restore and emergency procedure | Controlled failure and restore drills |
## Data handling defaults
| Data | Default location and retention | Access/purpose |
|---|---|---|
| Identity/role mapping | Customer stack, active account plus documented offboarding period | Authentication/administration; restricted operator access |
| Learning outcome | Customer stack, 180 days | Assignment and learning evaluation; no employment risk score |
| Voluntary feedback | Customer stack, minimise free text; 180 days maximum default | Learning improvement; aggregate reporting where possible |
| Raw packet payload | Disabled | Separate specific approval and purpose if ever enabled |
| Local metadata buffer | Edge, seven-day maximum and size cap | Reliable delivery/diagnosis; visible loss on overflow |
| Operational observation | Customer stack, 30 days | Security investigation; source and freshness preserved |
| Findings and audit | Customer stack, 180 days | Evidence, change history and accountability |
| Research export | Separate research environment, explicit project retention | Purpose-limited pseudonymised or approved data only |
| Backup | Separate encrypted backup, 30-day rolling expiry | Recovery; restore access restricted |
These are product defaults, not statutory periods. Before onboarding, document customer purpose, lawful basis, controller/processor roles, retention, subprocessors and international transfers. Adjust through configuration and approved policy. Pseudonymous events remain potentially personal data. Rights workflows must locate related records, export/correct/delete where applicable, propagate deletion to indexes and derived stores, and replay deletion tombstones after backup restoration. Immutable evidence needs a documented lawful retention exception rather than a blanket refusal to delete.
## Applicability matrix
| Framework | Relevant question | Required project action |
|---|---|---|
| GDPR | What personal data/purpose, roles and lawful basis apply? Is a DPIA required? | Processing inventory, minimisation, customer terms, rights process and risk assessment before pilot |
| EU AI Act | What is each feature's intended use and provider/deployer role? | Feature-level classification and oversight; no automatic assumption that all cybersecurity AI is high-risk |
| Portuguese cybersecurity regime/NIS2 | Is AegisAI or the customer in scope, and for which service? | Entity/service assessment and review of current implementing requirements |
| Cyber Resilience Act | Is a shipped software/appliance product in scope, and who is manufacturer/steward? | Product classification, vulnerability handling, update/support period and reporting readiness |
| NIST CSF/Cyber AI Profile | Which controls and AI-related risks are relevant? | Map Govern, Identify, Protect, Detect, Respond, Recover to evidence; label draft guidance accurately |
Sources: [GDPR](https://eur-lex.europa.eu/eli/reg/2016/679/oj/), [AI Act text](https://eur-lex.europa.eu/eli/reg/2024/1689/oj), [current Commission AI guidance](https://digital-strategy.ec.europa.eu/en/policies/regulatory-framework-ai), [CRA summary](https://digital-strategy.ec.europa.eu/en/policies/cra-summary), [NIST profile](https://www.nccoe.nist.gov/projects/cyber-ai-profile).
Workplace emotion recognition is subject to specific AI Act prohibitions and narrow exceptions; client products exclude biometric emotion inference. Consent is not treated as a universal workaround. Voluntary feedback and supportive UX remain possible design choices subject to ordinary data-purpose review.
CRA Article 14 reporting applies from 11 September 2026 for covered manufacturers; the Commission states general applicability from 11 December 2027. Those are external legal dates and do not move with project kickoff. Determine scope rather than assuming every SaaS function is automatically covered. [CRA reporting](https://digital-strategy.ec.europa.eu/en/policies/cra-reporting).
The CNCS notice previously reviewed reports the new Portuguese regime under Decree-Law 125/2025. Its linked notice produced a redirect loop in the 18 September refresh; obtain the authoritative text and current regulations during the applicability review before relying on detailed scope/deadlines. Do not reuse the old local legal memo as current authority. [CNCS notice](https://dyn.cncs.gov.pt/pt/detalhe/art/135998/novo-regime-juridico-da-ciberseguranca-entra-em-vigor).
## Risk register and accountable response
| Risk | Owner | Trigger / response |
|---|---|---|
| Portfolio exceeds lean-team capacity | PL | Support >20% for two sprints: pause expansion and fix operating burden |
| Legacy results cannot reproduce | RL | Keep claim excluded; publish limitation and rerun protocol |
| Training offers weak customer value | PL | Revisit content/package; do not claim efficacy from engagement |
| Upstream licence/enterprise cost changes | PS/PL | Recheck pinned bill of materials and quote; adjust adapter or package |
| Unacceptable false-alert burden | RL/PS | Keep model in shadow mode or remove it; use baseline |
| Agent authority bypass | PS | Block affected release, revoke capability and investigate |
| Industrial process impact | PS/customer operator | Keep passive-only; no active pilot without process-safety approval |
| Legal role or data purpose unclear | PL | Block affected processing, continue independent work, obtain scoped advice |
Legal review is targeted to actual intended use and customer commitments. Product documentation must describe supported evidence and controls without asserting certification, full compliance or insurer acceptance that has not been established.

## Slide 50
Regulatory applicability
Framework | Question to resolve
GDPR | Data purpose, roles, lawful basis, rights and DPIA
EU AI Act | Feature intended use and provider/deployer obligations
Portugal / NIS2 | Entity and service scope under current requirements
Cyber Resilience Act | Product scope, manufacturer role and reporting
NIST Cyber AI Profile | Control mapping with draft status clearly identified
Qualified applicability review precedes affected processing or shipment. No automatic compliance claim.
50
Notes: Regulatory applicability
GDPR / Data purpose, roles, lawful basis, rights and DPIA
EU AI Act / Feature intended use and provider/deployer obligations
Portugal / NIS2 / Entity and service scope under current requirements
Cyber Resilience Act / Product scope, manufacturer role and reporting
NIST Cyber AI Profile / Control mapping with draft status clearly identified
Project documentation: implementation-plan/11-security-privacy-regulation.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://eur-lex.europa.eu/eli/reg/2016/679/oj/
https://eur-lex.europa.eu/eli/reg/2024/1689/oj
https://digital-strategy.ec.europa.eu/en/policies/regulatory-framework-ai
https://digital-strategy.ec.europa.eu/en/policies/cra-summary
https://www.nccoe.nist.gov/projects/cyber-ai-profile
https://digital-strategy.ec.europa.eu/en/policies/cra-reporting
https://dyn.cncs.gov.pt/pt/detalhe/art/135998/novo-regime-juridico-da-ciberseguranca-entra-em-vigor

## Slide 51
Production readiness at every release
Common pilot requirements
Isolation, secrets, monitoring, restore evidence and scoped customer agreement.
General availability
Independent assessment, resolved critical/high findings, capacity and recovery evidence.
Product-specific acceptance
Useful learning, manageable alerts, safe validation or enforced agent authority.
Gate decision
Pass with evidence, reduce scope or move dependent work. All gates are currently pending.
51
Notes: Production readiness at every release
Common pilot requirements: Isolation, secrets, monitoring, restore evidence and scoped customer agreement.
General availability: Independent assessment, resolved critical/high findings, capacity and recovery evidence.
Product-specific acceptance: Useful learning, manageable alerts, safe validation or enforced agent authority.
Gate decision: Pass with evidence, reduce scope or move dependent work. All gates are currently pending.
Project documentation: implementation-plan/12-production-handbook.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
DETAILED PROJECT REFERENCE
# Production, pilot and release handbook
[Index](README.md) · Owner: Platform/Security Lead · All gates initially pending
## Gate evidence
| Gate | Target | Product-specific evidence, in addition to common controls |
|---|---|---|
| G1 | M3 Human Firewall pilot | Complete admin/learner journey, three interactive scenarios, reviewed programme, pilot protocol and onboarding rehearsal |
| G2 | M4–6 Human Firewall GA | Twelve reviewed scenarios, usable reports, operational support and customer value assessment; no unsupported efficacy claim |
| G3 | M7–9 Operations pilot | Asset/SBOM → finding → investigation → remediation evidence; source freshness/loss visible |
| G4 | M10–12 Operations GA | Measured alert workload, supported connectors, approval tests, 48-hour soak at agreed volume |
| G5 | M13–15 Defense Box pilot | Stable passive collection, approved validation, measured resource use and successful abort/cleanup |
| G6 | M16–18 Defense Box GA | Supported installation profile, upgrade/rollback, five checks and remediation retest evidence |
| G7 | M19–21 Agent Security pilot | Two customer workflows under enforced tool/identity/budget policies |
| G8 | M22–24 Agent Security GA | Isolation, revocation, injection/recovery evaluations, compatibility and cost accounting |
Common pilot controls: access/isolation tests, secrets inventory, monitoring, restore evidence, documented data purpose/retention, scoped agreement, support contact and rollback. Common GA controls: independent security assessment of the changed surface; all critical/high findings remediated and retested; load/capacity evidence; dependency/licence inventory; vulnerability process; runbooks; customer acceptance and release sign-off. No gate is marked passed by this document.
## Service objectives and support boundary
Engineering target: 99.9% monthly application availability, measured at the customer-facing service boundary with a declared measurement method. Client ISP/device downtime and upstream dependencies must be explained, not silently excluded from customer impact reports. A target becomes an SLA only after architecture, monitoring, staffing and contract review support it.
Pilot recovery targets: RPO 24 hours and RTO four hours. GA: RPO one hour and RTO four hours for managed application data, demonstrated by restore tests. These do not promise zero loss of unacknowledged edge buffers or restoration of the customer's own infrastructure. Implement point-in-time recovery or equivalent before claiming the tighter RPO.
Initial staffed support: Portuguese business hours, with named incident escalation arrangements in each pilot agreement. Automated monitoring may run continuously; this does not imply 24/7 staffed response. No numerical response SLA is sold before staffing is costed.
## Runbook: customer onboarding
1. PL confirms product scope, supported sources, buyer/operator, support hours and pilot outcomes.
2. PS records architecture, region, data purpose/retention, identity integration and permitted routes; legal/privacy review covers affected processing.
3. Deploy isolated stack from pinned manifests; rotate bootstrap secrets; verify backup and health.
4. Enrol only approved collectors/users; run positive and negative access tests.
5. Rehearse the principal customer journey and export evidence; document known limits and emergency contact.
6. Record baseline usage/cost and acceptance. Enable only purchased/approved modules.
## Runbook: release, upgrade and rollback
Build signed/versioned artefacts with dependency inventory and migration notes. Test in staging against a representative prior-version backup. Record irreversible migration risks and recovery path. Review release diff and permissions, take a verified backup, communicate the agreed maintenance window, deploy to a canary customer/test stack, and observe errors, job lag and data correctness before expansion. Roll back application/configuration only when schema compatibility permits; otherwise use the tested restore/forward-fix procedure. Never assume downgrade is safe after migration.
## Runbook: incident and credential compromise
Detect and classify affected customers/components; preserve necessary evidence and open an incident record. Restrict compromised credentials/workloads and isolate the affected execution boundary. Stop unsafe automation; inspect pending approvals and uncertain side effects. Restore known-good operation, verify integrity and reconcile jobs. PL coordinates contractual/regulatory communications after applicability review; this handbook does not send any notifications. Record timeline, root cause, customer impact and corrective tests.
If control-plane connectivity is lost, do not assume a policy revocation reached the edge. Use the documented local enforcement/emergency path and record confirmation. Restoration includes verification that stale credentials and rules are not re-enabled.
## Runbook: backup restoration and data rights
Restore to an isolated environment, verify integrity and timestamps, measure actual RPO/RTO, replay deletion tombstones, rotate credentials where exposure is possible, and test application/connector behaviour before making the restored environment active. Retain a signed exercise record with backup identity, operator, duration and discrepancies. Perform before each GA and after material storage changes; schedule periodic operational drills after launch.
Rights/offboarding: verify requester authority, export permitted records, revoke users/collectors/provider mappings, remove routes, disable jobs, purge active data under agreed policy and expire backups on schedule. Document retained legal evidence and deletion timing. Ensure the customer can uninstall the edge component without residual trust.
## Runbook: validation and agent execution
Validate target/task scope, authority, expiry, resource limits and cleanup before starting. Monitor heartbeats and budget. Abort on out-of-scope access, safety trigger, loss of required control, or operator request. Preserve partial results and cleanup status. Reconcile external effects before retries. Agent audit replay must not execute tools. Rotate task credentials after completion or suspected compromise.
## Release record template
Record: product/version; gate; owner/reviewer; deployment and schema versions; source/model versions; supported capacity; test artefacts; security assessment/retests; restore/rollback evidence; customer acceptance; cost/support profile; unresolved low/medium risks and owners; final go/no-go decision. A failed material criterion results in no-go or reduced scope, not an undocumented exception.

## Slide 52
Operating targets and runbooks
Area | Planning requirement
Availability | 99.9% monthly application target before any contractual SLA
Pilot recovery | 24-hour recovery point and four-hour recovery time
GA recovery | One-hour recovery point and four-hour recovery time
Support | Portuguese business hours with named escalation arrangements
Runbooks | Onboard, upgrade, roll back, respond, restore and offboard
Targets require measured evidence and staffing. Continuous monitoring does not imply 24/7 staffed response.
52
Notes: Operating targets and runbooks
Availability / 99.9% monthly application target before any contractual SLA
Pilot recovery / 24-hour recovery point and four-hour recovery time
GA recovery / One-hour recovery point and four-hour recovery time
Support / Portuguese business hours with named escalation arrangements
Runbooks / Onboard, upgrade, roll back, respond, restore and offboard
Project documentation: implementation-plan/12-production-handbook.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.

## Slide 53
Kickoff decisions and immediate actions
People and schedule
Assign role owners and record the kickoff date.
First sprint
Create issues for the first 90 days using the existing task IDs and acceptance criteria.
Customer discovery
Confirm interview candidates, buying roles and pilot selection criteria.
External validation
Resolve provider terms, processing roles and model licences before the relevant commitment.
53
Notes: Kickoff decisions and immediate actions
People and schedule: Assign role owners and record the kickoff date.
First sprint: Create issues for the first 90 days using the existing task IDs and acceptance criteria.
Customer discovery: Confirm interview candidates, buying roles and pilot selection criteria.
External validation: Resolve provider terms, processing roles and model licences before the relevant commitment.
Project documentation: implementation-plan/14-decisions.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.

## Slide 54
Technical reference
Architecture continuity and implementation detail
Appendix for team discussion and follow-up
Detailed source extracts appear in speaker notes
Notes: Technical reference
Architecture continuity and implementation detail
Project documentation: implementation-plan/02-source-traceability.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
DETAILED PROJECT REFERENCE
# Source assessment and traceability
[Index](README.md) · Owner: Product Lead and Research Lead
## Source inventory and interpretation
| ID | Local source | Retained context | Revision needed |
|---|---|---|---|
| L01 | [AegisAI Project Blueprint](../AegisAI%20Project%20Blueprint.pdf) | Integrated SME security; human and technical protection; SCA, UEBA, simulations, recovery, future OT and partnerships | Remove old dates, blanket efficacy/compliance claims, and assumption that every function ships together |
| L02 | [Work packages](../workpackages.pdf) | WP1–7, Human Boundary Ecosystem, local processing, data rights and SME operation | Extend beyond training; retain governance throughout all products |
| L03 | [Platform architecture](../platform-architecture-doc.md) | Thirteen layers; five integrated squad products; packaging, federation and five research areas | Bring operational foundations forward; use one product stream; replace framework/version prescriptions with evaluated choices |
| L04 | [Research paper](../aegisai_icsa_2026_latest.pdf) | Existing experimental hypotheses and results | Reconcile dataset versions, real/synthetic labels, splits and reported metrics before reuse |
| L05 | [Regulatory analysis](../AEGISAE_EU_Portugal_Regulatory_Analysis.docx) | Portuguese/EU market and governance questions | Recheck current law and intended-use applicability; remove generic high-risk-AI classification and automatic-compliance implications |
| L06 | [NIST Cyber AI document](../cybersecurity-framework-for-ai.pdf) | Secure, Defend and Thwart perspectives across cybersecurity governance | Keep preliminary-draft status visible; use current publication status from evidence register |
| L07 | [Perplexity note](../perplexity-deepsearch.md) | Model/tool contracts, provenance, scientific writing, local routing | Validate citations and model/hardware claims; use as design input |
| L08 | [GPT note](../gpt-deepsearch.md) | Agent engineering and research environment ideas | Compare against bounded workflow baseline; no automatic adoption of every framework |
| L09 | [Gemini note](../gemini-deepsearch.md) | Local agent workspace and reusable infrastructure | Proposed names and technology stacks are suggestions, not accepted branding or proven requirements |
| L10 | [Deep research report (4)](../deep-research-report%20(4).md) | Persistent state, memory, capability controls, browser tools, long-duration agents, evaluation and agent training | Replace the full frontier-platform-in-90-days proposal with staged internal validation and later Agent Security commercialisation |
| L11 | [Approved portfolio plan](../plan.md) | Latest user-approved sequence and 24-month direction | Expanded by this pack; preserve original as decision history |
Read-only inspection also found a Docusaurus portal under the parent source tree and Python experiments under the parent research tree. This pack does not modify those assets. The inspected research reports and code are prototypes, not evidence of an operating client product.
### Reproducibility issues to resolve
The inspected fusion report describes Mock-CERT results that differ from the paper's reported metrics. Some code paths contain placeholder or generated labels when ground truth is absent. Separate real-data loader paths also exist; do not infer that every result uses the fallback. R0 must map each published result to its exact execution path and dataset. Synthetic phishing/emotion outputs demonstrate a simulated mechanism, not effectiveness with employees. Preserve the historical results and label their scope rather than rewriting them to imply stronger evidence.
## Blueprint capability mapping
| ID | Original capability | Disposition and reason | Destination |
|---|---|---|---|
| B01 | Asset discovery and inventory | Retained; imported/passive evidence first, explicit scope for active discovery | Security Operations, G3–G4 |
| B02 | Software composition and dependencies | Retained; SBOM/advisory ingestion and remediation tracking | Security Operations, G3–G4 |
| B03 | Gamification and role-based training | Retained; supportive mechanics and validated content | Human Firewall, G1–G2 |
| B04 | User/entity baselines and drift | Revised; alert utility instead of personal risk rankings | R2; Security Operations after validation |
| B05 | Relationship/social graph analytics | Research-only initially; no social surveillance by default | R2, months 7–12 |
| B06 | Cross-domain event correlation | Retained with limited initial connectors | Security Operations, G3–G4 |
| B07 | 24/7 AI hunting | Revised to continuous collection/rules with explicit service hours; no 24/7 human SOC promise | Security Operations |
| B08 | Access recommendations | Retained as evidence-backed proposals; no training-score denial | Security Operations; shared approvals |
| B09 | Automated containment | Revised to approved, scoped actions; deterministic pre-authorised automation considered later | G4 onward |
| B10 | Guided remediation | Retained with execution/verification evidence | Security Operations |
| B11 | Adversarial simulation/GANs | Revised; safe scripted baseline before generative methods | Defense Box, R4 |
| B12 | Explainable alerts | Revised; provenance, features and uncertainty rather than claimed faithful chain-of-thought | All products, R3 |
| B13 | Local lightweight models | Retained where measured quality and resource use justify them | Workspace, edge, R5 |
| B14 | Central Synaptic Data Lake | Revised to classified evidence storage and local raw telemetry; no universal raw-data centralisation | Shared architecture |
| B15 | Federated intelligence/privacy | Research-only until local utility, permissions and privacy threat model exist | R5, months 16–24 |
| B16 | Integrity monitoring | Retained via selected collector integration | Security Operations/Defense Box |
| B17 | Recovery and resilience drills | Retained; runbooks and restore evidence precede simulations | Every gate; Defense Box |
| B18 | Compliance/national frameworks | Retained as traceable evidence mapping, not certification | WP5 and reports |
| B19 | IoT/OT monitoring | Deferred customer deployment; passive lab before scoped pilot | Months 16–24, conditional |
| B20 | Cyber-insurance integration | Deferred partnership discovery and evidence export | Months 22–24; no discount promise |
| B21 | MSP channel and enterprise integration | Retained after direct SME validation | WP6/WP8; G4 onward |
| B22 | Angola/Lusophone expansion | Deferred market validation after Portuguese retention and support economics | Months 22–24 strategy |
## All thirteen architecture layers
| Layer | Disposition | Implementation destination |
|---|---|---|
| 1 Training/dynamic testing UI | Retained; defer immersive 3D until evidence of value | Human Firewall |
| 2 Multi-agent orchestration | Revised; bounded single workflows first | Internal workspace, R6, Agent Security |
| 3 LLM/classical ML | Retained; benchmark before selection/fine-tuning | Research/model adapter |
| 4 Local SLM | Retained; no assumed zero leakage or fixed latency | Edge/workspace, R5 |
| 5 SNA/UEBA | Revised; operational findings and controlled graph research | Security Operations, R2 |
| 6 XAI/AI UX | Revised to evidence-grounded explanation | Shared evidence UI, R3 |
| 7 GAN/adversarial components | Revised; GAN is experimental candidate, not dependency | Defense Box, R4 |
| 8 Workflow automation | Retained; persistent jobs and approvals before multiple workflow engines | Shared platform |
| 9 Monitoring/traceability | Retained and brought into month 1 | WP9, all gates |
| 10 Security/privacy | Retained; advanced cryptography conditional on threat model | WP5/WP7; R5 |
| 11 Integration | Retained; small connector set and versioned contracts | WP6, API/SDK |
| 12 Defense Box | Retained as software appliance before custom hardware | G5–G6 |
| 13 Desktop integration | Revised; edge service first, desktop shell if offline/install needs warrant | Defense Box/Agent Security |
Packaging/deployment appears outside the numbered layers in the source diagram. It is retained as WP9 from month 1, rather than delayed until portfolio integration.
## Five original integrated squad products
| Original squad | Disposition | Destination |
|---|---|---|
| Intelligent Training System | Retained; decouple from UEBA risk scoring | Human Firewall, G1–G2 |
| Adversarial Testing Platform | Retained; safe emulation and retest evidence | Defense Box and Validation, G5–G6 |
| Privacy-First Analytics | Combined with local detection; federation remains conditional research | Security Operations + R5 |
| Enterprise Integration Hub | Combined into shared adapters, approvals and response workflows | Security Operations, later enterprise packaging |
| Desktop Security Assistant | Combined into edge/local AI capabilities; standalone endpoint protection claims deferred | Defense Box + Agent Security |
WP1–7 are all preserved and expanded in the [work-package register](09-work-packages.md). Research continuity is specified in [R0–R6](06-research-programme.md), including human factors, explainability, federation and empathic UX. Old promises such as zero false positives, fixed detection percentages, or improvements for every federation participant become hypotheses with baselines and confidence intervals.

## Slide 55
Architecture layers 1–7
Original layer | Current destination
1 Training UI | Human Firewall with accessible web delivery
2 Agent orchestration | Internal workflows, then Agent Security
3–4 Models and local SLMs | Evaluated model adapters and edge inference
5 SNA / UEBA | Security Operations research and shadow mode
6–7 XAI and adversarial generation | Evidence-based explanation and controlled validation
55
Notes: Architecture layers 1–7
1 Training UI / Human Firewall with accessible web delivery
2 Agent orchestration / Internal workflows, then Agent Security
3–4 Models and local SLMs / Evaluated model adapters and edge inference
5 SNA / UEBA / Security Operations research and shadow mode
6–7 XAI and adversarial generation / Evidence-based explanation and controlled validation
Project documentation: implementation-plan/02-source-traceability.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.

## Slide 56
Architecture layers 8–13
Original layer | Current destination
8 Workflow automation | Persistent jobs and reviewed actions
9–10 Observability and privacy | Shared platform from the first release
11 Integrations | Versioned adapters and conformance tests
12 Defense Box | Software appliance before custom hardware
13 Desktop integration | Edge service first, shell if needed
56
Notes: Architecture layers 8–13
8 Workflow automation / Persistent jobs and reviewed actions
9–10 Observability and privacy / Shared platform from the first release
11 Integrations / Versioned adapters and conformance tests
12 Defense Box / Software appliance before custom hardware
13 Desktop integration / Edge service first, shell if needed
Project documentation: implementation-plan/02-source-traceability.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.

## Slide 57
The five original integrated products
Original squad product | Revised destination
Intelligent Training System | Human Firewall without compulsory UEBA scoring
Adversarial Testing Platform | Defense Box and Validation
Privacy-First Analytics | Local detection plus conditional federation research
Enterprise Integration Hub | Shared adapters, approvals and response workflows
Desktop Security Assistant | Edge/local AI in Defense Box and Agent Security
57
Notes: The five original integrated products
Intelligent Training System / Human Firewall without compulsory UEBA scoring
Adversarial Testing Platform / Defense Box and Validation
Privacy-First Analytics / Local detection plus conditional federation research
Enterprise Integration Hub / Shared adapters, approvals and response workflows
Desktop Security Assistant / Edge/local AI in Defense Box and Agent Security
Project documentation: implementation-plan/02-source-traceability.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.

## Slide 58
Longer-term capabilities remain in scope
Capability | Entry condition
Federated intelligence | Useful local models, participants and privacy controls
Industrial / IoT monitoring | Passive lab evidence and an operator-sponsored safe pilot
Insurance evidence | Partner demand and permitted evidence exchange
Lusophone expansion | Portuguese retention and support economics
Advanced automation | Measured benefit with bounded authority and rollback
58
Notes: Longer-term capabilities remain in scope
Federated intelligence / Useful local models, participants and privacy controls
Industrial / IoT monitoring / Passive lab evidence and an operator-sponsored safe pilot
Insurance evidence / Partner demand and permitted evidence exchange
Lusophone expansion / Portuguese retention and support economics
Advanced automation / Measured benefit with bounded authority and rollback
Project documentation: implementation-plan/02-source-traceability.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.

## Slide 59
Default data retention
Data | Planning default
Local metadata buffer | Seven days with a size cap
Operational observations | 30 days in the customer stack
Findings, audit and learning outcomes | 180 days
Raw packet payload | Disabled by default
Encrypted backups | 30-day rolling expiry with deletion replay
These are adjustable product defaults, not statutory retention periods.
59
Notes: Default data retention
Local metadata buffer / Seven days with a size cap
Operational observations / 30 days in the customer stack
Findings, audit and learning outcomes / 180 days
Raw packet payload / Disabled by default
Encrypted backups / 30-day rolling expiry with deletion replay
Project documentation: implementation-plan/11-security-privacy-regulation.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://eur-lex.europa.eu/eli/reg/2016/679/oj/
https://eur-lex.europa.eu/eli/reg/2024/1689/oj
https://digital-strategy.ec.europa.eu/en/policies/regulatory-framework-ai
https://digital-strategy.ec.europa.eu/en/policies/cra-summary
https://www.nccoe.nist.gov/projects/cyber-ai-profile
https://digital-strategy.ec.europa.eu/en/policies/cra-reporting
https://dyn.cncs.gov.pt/pt/detalhe/art/135998/novo-regime-juridico-da-ciberseguranca-entra-em-vigor

## Slide 60
Contract and failure tests
Scenario | Expected behaviour
Wrong organisation or revoked identity | Deny access, including nested evidence references
Duplicate, late or unsupported event | Deduplicate, preserve timing or reject explicitly
Expired or changed approval | Require a new valid approval
Lost response after side effect | Reconcile before retry
Offline source or stale feed | Show uncertainty, last success and loss counters
60
Notes: Contract and failure tests
Wrong organisation or revoked identity / Deny access, including nested evidence references
Duplicate, late or unsupported event / Deduplicate, preserve timing or reject explicitly
Expired or changed approval / Require a new valid approval
Lost response after side effect / Reconcile before retry
Offline source or stale feed / Show uncertainty, last success and loss counters
Project documentation: implementation-plan/05-interface-contracts.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.

## Slide 61
Research promotion record
Evidence item | Required record
Data and method | Provenance, rights, split, labels and baseline
Reproduction | Code, configuration, seed, dependencies and output
Operational evaluation | Cost, failure cases, utility and uncertainty
Product integration | Feature flag, monitoring and rollback
Approval | Research, security and product-owner review
61
Notes: Research promotion record
Data and method / Provenance, rights, split, labels and baseline
Reproduction / Code, configuration, seed, dependencies and output
Operational evaluation / Cost, failure cases, utility and uncertainty
Product integration / Feature flag, monitoring and rollback
Approval / Research, security and product-owner review
Project documentation: implementation-plan/06-research-programme.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://www.sysnet.ucsd.edu/~voelker/pubs/phishtrain-oakland25.pdf
https://www.nist.gov/blogs/cybersecurity-insights/privacy-attacks-federated-learning

## Slide 62
Current evidence and developments
Source | Relevance
NetBird Draft Mode, September 2026 | Reviewable changes and policy UX
NetBird Norsk Helsenett case, August 2026 | Organisational provisioning and support needs
AgentFlow, August 2026 | Policy and data-flow research
AgentLAB / AMA-Bench, February 2026 | Long-horizon attacks and memory evaluation
Field training study, IEEE S&P 2025 | Controlled evaluation of learning effectiveness
Sources and URLs appear in speaker notes. Vendor cases and preprints retain their limitations.
62
Notes: Current evidence and developments
NetBird Draft Mode, September 2026 / Reviewable changes and policy UX
NetBird Norsk Helsenett case, August 2026 / Organisational provisioning and support needs
AgentFlow, August 2026 / Policy and data-flow research
AgentLAB / AMA-Bench, February 2026 / Long-horizon attacks and memory evaluation
Field training study, IEEE S&P 2025 / Controlled evaluation of learning effectiveness
Project documentation: implementation-plan/13-evidence-register.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
External references in the underlying source:
https://docs.netbird.io/about-netbird/how-netbird-works
https://docs.netbird.io/manage/networks/how-routing-peers-work
https://docs.netbird.io/selfhosted/enterprise
https://github.com/netbirdio/netbird/blob/main/LICENSE
https://netbird.io/pricing
https://docs.netbird.io/agent-network
https://docs.netbird.io/agent-network/how-it-works
https://docs.netbird.io/agent-network/quickstart
https://tailscale.com/pricing
https://www.firezone.dev/pricing
https://wazuh.com/cloud/
https://netbird.io/knowledge-hub/control-center-draft-mode
https://netbird.io/knowledge-hub/norsk-helsenett
https://netbird.io/knowledge-hub/security-advisory-daemon-ipc-local-privilege-escalation
https://tailscale.com/blog/aperture-public-beta
https://www.knowbe4.com/press/knowbe4-launches-aida-orchestration-as-the-first-fully-autonomous-agent-for-human-risk-management
https://wazuh.com/resources/case-studies/digifors-mssp-services/
https://digital-strategy.ec.europa.eu/en/policies/cra-reporting
https://www.sysnet.ucsd.edu/~voelker/pubs/phishtrain-oakland25.pdf
https://arxiv.org/abs/2602.16901
https://arxiv.org/abs/2602.22769
https://arxiv.org/abs/2608.22868
https://www.anthropic.com/engineering/demystifying-evals-for-ai-agents
https://www.anthropic.com/engineering/building-c-compiler
https://www.nist.gov/blogs/cybersecurity-insights/privacy-attacks-federated-learning
https://docs.openhands.dev/sdk/arch/security
https://cyclonedx.org/specification/overview/
https://osv.dev/
https://github.com/apache/caldera
https://attack.mitre.org/tactics/ics/
https://attack.mitre.org/mitigations/ics/
https://www.enisa.europa.eu/publications/nis-investments-2025
https://www.enisa.europa.eu/news/nis360-the-bigger-picture-on-maturity-and-criticality-of-nis-critical-sectors
https://dyn.cncs.gov.pt/pt/detalhe/art/135998/novo-regime-juridico-da-ciberseguranca-entra-em-vigor
https://eur-lex.europa.eu/eli/reg/2016/679/oj/
https://eur-lex.europa.eu/eli/reg/2024/1689/oj
https://digital-strategy.ec.europa.eu/en/policies/regulatory-framework-ai
https://digital-strategy.ec.europa.eu/en/policies/cra-summary
https://www.nccoe.nist.gov/projects/cyber-ai-profile
https://www.nccoe.nist.gov/publications/csf-profile/nist-ir-8596-ipd-cybersecurity-framework-profile-artificial-intelligence
DETAILED PROJECT REFERENCE
# Evidence register, current developments and research path
[Index](README.md) · Research snapshot: 17–18 September 2026 · Owner: Research Lead
This is a curated primary-source register, not an exhaustive literature review or a claim that every linked technology has been tested. Publication date, page update and access date are different. “Living” means no fixed publication date is relied upon. An unavailable page is explicitly marked. Recheck mutable documentation, pricing and law at adoption. Local-source inventory is in [traceability](02-source-traceability.md).
## Networking, agent access and business
| ID | Source / publisher | Publication or update; accessed | Type and supported use | Limitation / project action |
|---|---|---|---|---|
| E01 | [How NetBird works — NetBird](https://docs.netbird.io/about-netbird/how-netbird-works) | Updated 2026-08-21; 2026-09-18 | Official architecture; client/control/data-plane explanation | Contains old/new relay context; use release-matched deployment docs |
| E02 | [Routing peers — NetBird](https://docs.netbird.io/manage/networks/how-routing-peers-work) | Living; 2026-09-17 | Official forwarding/NAT design | Overlay protection does not describe the entire LAN path; test routing |
| E03 | [Self-hosted enterprise — NetBird](https://docs.netbird.io/selfhosted/enterprise) | Updated 2026-09-16; 2026-09-18 | Official feature, isolation and operating constraints | Commercial terms require confirmation for intended customer model |
| E04 | [Repository licence — NetBird](https://github.com/netbirdio/netbird/blob/main/LICENSE) | Living main branch; 2026-09-17 | Primary licence text | Pin release and inspect all distributed components |
| E05 | [Cloud pricing — NetBird](https://netbird.io/pricing) | Living; 2026-09-18 | Vendor pricing snapshot | Cloud EUR values are not self-hosted quotes; no resale assumption |
| E06 | [Agent Network overview — NetBird](https://docs.netbird.io/agent-network) | June 2026 page; 2026-09-17 | Official beta/product status | Internal experiment, not first-release dependency |
| E07 | [Agent Network architecture — NetBird](https://docs.netbird.io/agent-network/how-it-works) | Living; 2026-09-17 | Official proxy/direct-resource distinction | Application/tool permission still required |
| E08 | [Agent Network quickstart — NetBird](https://docs.netbird.io/agent-network/quickstart) | Updated 2026-06-30; 2026-09-17 | Official release-candidate setup | Do not apply beta defaults to client production |
| E09 | [Pricing — Tailscale](https://tailscale.com/pricing) | Living; 2026-09-18 | Vendor packaging comparison | Billing and free-use restrictions change; refresh before quote |
| E10 | [Pricing — Firezone](https://www.firezone.dev/pricing) | Living; 2026-09-18 | Vendor free/team/enterprise comparison | Does not by itself establish repository licence rights |
| E11 | [Cloud — Wazuh](https://wazuh.com/cloud/) | Living; 2026-09-18 | Managed open-source security offering | Compare service scope and operating cost, not price alone |
## Recent news and use cases
Selected developments available at research time; “recent” does not mean a complete worldwide news feed.
| ID / date | Source | What it changes for AegisAI |
|---|---|---|
| N01 · 2026-09-04 | [NetBird Control Center Draft Mode](https://netbird.io/knowledge-hub/control-center-draft-mode) | Vendor product update: reviewable configuration changes are a useful UX reference. AegisAI should bind approvals to durable proposed changes and execution evidence. |
| N02 · 2026-08-03 | [NetBird / Norsk Helsenett case](https://netbird.io/knowledge-hub/norsk-helsenett) | Vendor case: provisioning, identity and operational simplicity matter in organisational adoption. It does not validate our future healthcare readiness. |
| N03 · 2026-07-30 | [NetBird client-daemon security advisory](https://netbird.io/knowledge-hub/security-advisory-daemon-ipc-local-privilege-escalation) | Primary vendor advisory: include local privileged-service attack surfaces and patch management in the edge threat model. Select a currently supported patched release at adoption. |
| N04 · 2026-04-23 | [Tailscale Aperture beta](https://tailscale.com/blog/aperture-public-beta) | Vendor announcement: networking companies are expanding into AI access governance; validate task-level control differentiation. |
| N05 · 2026-02-24 | [KnowBe4 AIDA orchestration launch](https://www.knowbe4.com/press/knowbe4-launches-aida-orchestration-as-the-first-fully-autonomous-agent-for-human-risk-management) | Vendor announcement: autonomous training orchestration is an established competitive claim, not our unique novelty. |
| N06 · Date not relied upon | [Wazuh / DigiFors MSSP case](https://wazuh.com/resources/case-studies/digifors-mssp-services/) | Vendor case: services and supported integrations can form a business around an open platform. Validate our own margins. |
| N07 · Updated 2026-09-11 | [Commission CRA reporting guidance](https://digital-strategy.ec.europa.eu/en/policies/cra-reporting) | Official update: relevant reporting provisions are now in application; assess product/manufacturer scope early. |
All N01–N07 links were opened on 2026-09-18. These entries are not evidence of independent outcome audits or guaranteed future availability.
## Research and frontier agents
| ID | Source | Date / access | Evidence and decision |
|---|---|---|---|
| R01 | [Understanding the Efficacy of Phishing Training in Practice — Ho et al.](https://www.sysnet.ucsd.edu/~voelker/pubs/phishtrain-oakland25.pdf) | IEEE S&P 2025; 2026-09-18 | Primary field study; limited benefits in its setting. Use control comparisons and delayed outcomes, not assumed efficacy. |
| R02 | [AgentLAB](https://arxiv.org/abs/2602.16901) | 2026-02 preprint; 2026-09-18 | Long-horizon agent attacks; informs R6 adversarial task design. Benchmark transfer remains unproven. |
| R03 | [AMA-Bench](https://arxiv.org/abs/2602.22769) | 2026-02 preprint; 2026-09-18 | Memory evaluation; compare explicit state/retrieval before increasing memory complexity. |
| R04 | [AgentFlow](https://arxiv.org/abs/2608.22868) | 2026-08 preprint; 2026-09-18 | Policy/data-flow enforcement; test independent authorisation and evidence provenance. Research results are not universal safety guarantees. |
| R05 | [Demystifying evals for AI agents — Anthropic](https://www.anthropic.com/engineering/demystifying-evals-for-ai-agents) | 2026-01; 2026-09-18 | First-party engineering guidance; evaluate complete workflows, repeated runs and failure recovery. |
| R06 | [Building a C compiler — Anthropic](https://www.anthropic.com/engineering/building-c-compiler) | 2026-02-05; 2026-09-18 | First-party multi-agent engineering account; useful as a scale/cost caution, not a lean-team requirement. |
| R07 | [Privacy attacks in federated learning — NIST](https://www.nist.gov/blogs/cybersecurity-insights/privacy-attacks-federated-learning) | 2024-01-24; 2026-09-18 | Official research discussion: updates and trained models can leak data. Design and evaluate privacy protections rather than assuming federation is sufficient. |
| R08 | [OpenHands security architecture](https://docs.openhands.dev/sdk/arch/security) | Living; 2026-09-18 | Official runtime controls; benchmark independently and enforce deterministic boundaries outside model judgement. |
Prioritised research path: R0 evidence repair → R1 human outcomes + R6 internal agent baseline → R2/R3 operational detection/explanation → R4/R5 local validation → external R6 product evaluation and conditional federation/OT. Follow citations into primary methods and datasets; do not treat AI-generated local notes as authoritative references. Record model, dataset and benchmark revisions at every experimental run.
## Security operations, validation and industrial foundations
| ID | Source | Date / access | Use and limitation |
|---|---|---|---|
| T01 | [CycloneDX specification overview](https://cyclonedx.org/specification/overview/) | Living; 2026-09-18 | SBOM contract reference; implementation must declare supported schema version |
| T02 | [OSV](https://osv.dev/) | Living; 2026-09-18 | Advisory source/API ecosystem; missing match does not prove absence of exposure |
| T03 | [Apache Caldera repository](https://github.com/apache/caldera) | Living; 2026-09-18 | Original MITRE URL redirected here during review; validate current release/licence before reuse |
| T04 | [ATT&CK for ICS tactics — MITRE](https://attack.mitre.org/tactics/ics/) | Living; 2026-09-18 | Threat taxonomy; not an active-test authorisation |
| T05 | [ATT&CK for ICS mitigations — MITRE](https://attack.mitre.org/mitigations/ics/) | Living; 2026-09-18 | Industrial control/safety context; validate techniques in representative lab first |
## Market, law and governance
| ID | Source | Date / access | Claim supported / limit |
|---|---|---|---|
| G01 | [NIS Investments 2025 — ENISA](https://www.enisa.europa.eu/publications/nis-investments-2025) | 2025-12-08; 2026-09-18 | Official survey with predominantly large organisations; not representative SME pricing evidence |
| G02 | [NIS360 maturity update — ENISA](https://www.enisa.europa.eu/news/nis360-the-bigger-picture-on-maturity-and-criticality-of-nis-critical-sectors) | 2026-05-28; 2026-09-17 | Sector maturity context; local buyer discovery remains necessary |
| G03 | [Portuguese regime notice — CNCS](https://dyn.cncs.gov.pt/pt/detalhe/art/135998/novo-regime-juridico-da-ciberseguranca-entra-em-vigor) | 2026-04-06; read 2026-09-17, refresh failed 2026-09-18 | Official notice; redirect loop on refresh. Obtain authoritative decree/current regulations before scope advice |
| G04 | [GDPR — EUR-Lex](https://eur-lex.europa.eu/eli/reg/2016/679/oj/) | Regulation 2016/679; searched 2026-09-18 | Primary legislation: data purpose, rights, processor roles, DPIA; apply to actual processing |
| G05 | [AI Act — EUR-Lex](https://eur-lex.europa.eu/eli/reg/2024/1689/oj) | Regulation 2024/1689; searched 2026-09-18 | Primary legislation; feature/intended-use classification, including workplace emotion restrictions |
| G06 | [AI regulatory framework — Commission](https://digital-strategy.ec.europa.eu/en/policies/regulatory-framework-ai) | Living; 2026-09-18 | Current implementation context; check amended/consolidated law before legal deadlines are promised |
| G07 | [CRA legislative summary — Commission](https://digital-strategy.ec.europa.eu/en/policies/cra-summary) | Living; 2026-09-18 | General and phased applicability; determine software/appliance scope and responsible role |
| G08 | [Cyber AI Profile — NIST NCCoE](https://www.nccoe.nist.gov/projects/cyber-ai-profile) | Living; 2026-09-18 | Development/status reference; draft guidance is not certification |
| G09 | [NIST IR 8596 initial preliminary draft](https://www.nccoe.nist.gov/publications/csf-profile/nist-ir-8596-ipd-cybersecurity-framework-profile-artificial-intelligence) | Preliminary draft; 2026-09-18 | Status of source framework; track next version rather than implying final standard |
## Evidence gaps and maintenance
Open items: actual customer willingness to pay, named pilot partners, hosting/licence quotations, per-product legal applicability, model hardware benchmarks, reproducible legacy result mapping and independent product security tests. None is silently filled with vendor claims or invented numbers.
RL reviews literature quarterly and before a research promotion; PL refreshes competitors/pricing before packaging decisions; PS checks upstream releases/advisories before adoption and during the future operating lifecycle. This pack does not create a scheduled monitor. New entries must identify source type, publication/update date if known, access status, precise supported claim, limitation and affected decision.

## Slide 63
Documentation and team follow-through
Implementation handbook
The index links 19 documents covering product, research and operations.
Source traceability
All 13 layers, five squad products and original work packages have a destination.
Delivery control
Task IDs, owner roles, dependencies and gate evidence guide implementation.
Team cadence
Two-week product reviews, monthly research/commercial reviews and release sign-off.
63
Notes: Documentation and team follow-through
Implementation handbook: The index links 19 documents covering product, research and operations.
Source traceability: All 13 layers, five squad products and original work packages have a destination.
Delivery control: Task IDs, owner roles, dependencies and gate evidence guide implementation.
Team cadence: Two-week product reviews, monthly research/commercial reviews and release sign-off.
Project documentation: implementation-plan/README.md
Documentation baseline: 18 September 2026. Schedule values are targets measured from kickoff.
DETAILED PROJECT REFERENCE
# AegisAI implementation and research handbook
Version 1.0 · Prepared 18 September 2026 · Owner: Product Lead
**Status: approved direction translated into implementation specifications. Product development, customer validation, security testing, and legal applicability reviews remain future work.** Nothing in this pack certifies an existing production deployment.
AegisAI will build four independently usable products on a shared platform: Human Firewall in months 3–6, Security Operations in months 10–12, Defense Box and Validation in months 16–18, and Agent Security in months 22–24. Months run from an explicitly recorded future kickoff, not from the date of this document. Release gates control progression.
NetBird is an architectural and commercial reference and an optional upstream connectivity provider. AegisAI owns its product experience, evidence model, integrations, intelligence, and lifecycle. Training is not a prerequisite for the other products.
## Reading order
| Document | Decisions and practical use |
|---|---|
| [Portfolio strategy](01-portfolio-strategy.md) | Customers, product sequence, ownership, scope and assumptions |
| [Source assessment and traceability](02-source-traceability.md) | Original blueprint, WP1–7, all 13 layers and five squad products; retained and revised ambitions |
| [Shared architecture](03-shared-architecture.md) | Trust boundaries, deployment, data flows and build/reuse choices |
| [NetBird study](04-netbird-study.md) | How it works, limitations, component reuse, integration and business lessons |
| [Interface contracts](05-interface-contracts.md) | Versioned API design, event envelope, jobs, approvals and adapter boundaries |
| [Human Firewall](products/01-human-firewall.md) | Months 1–6 specification, backlog and release acceptance |
| [Security Operations](products/02-security-operations.md) | Months 7–12 specification, backlog and release acceptance |
| [Defense Box and Validation](products/03-defense-box.md) | Months 13–18 specification, backlog and release acceptance |
| [Agent Security](products/04-agent-security.md) | Months 19–24 specification, backlog and release acceptance |
| [Research programme](06-research-programme.md) | Experiments, baselines, evaluation protocols and promotion rules |
| [Internal agent workspace](07-internal-agent-workspace.md) | Early research/engineering tooling, model evaluation and containment |
| [Roadmap and first 90 days](08-roadmap-backlog.md) | Milestones, dependencies, ownership and capacity rules |
| [Work packages](09-work-packages.md) | WP1–10 deliverables, acceptance and responsibilities |
| [Market and commercial model](10-market-business-model.md) | Competitors, discovery, pricing hypotheses, costs, open-core boundary |
| [Security, privacy and regulation](11-security-privacy-regulation.md) | Threat model, data handling, legal applicability and risk register |
| [Production and pilot handbook](12-production-handbook.md) | Release gates, runbooks, customer lifecycle and support |
| [Evidence and current developments](13-evidence-register.md) | Primary sources, dated news, use cases and limitations |
| [Decision register](14-decisions.md) | Accepted defaults, revisit triggers and outstanding external validations |
## How to use this pack
1. Assign actual people to the owner roles and record kickoff in the [roadmap](08-roadmap-backlog.md).
2. Import only the first-90-day backlog into the chosen issue tracker; preserve task IDs and acceptance evidence.
3. Store implementation and test artefacts against their task and release gate. A checkbox without evidence does not close a gate.
4. Review scope every two weeks, customer value monthly, and portfolio progression at each release gate.
5. Update source dates and legal/pricing checks before a customer commitment. Evidence is a dated snapshot, not a monitoring service.
## Evidence conventions
- **Local:** a project source or inspected prototype; does not establish external validity.
- **Primary research:** authors' paper or original study; preprints are labelled and findings remain bounded by evaluation conditions.
- **Official documentation:** upstream functionality or standards information; verify the pinned version during implementation.
- **Vendor claim/case:** vendor-reported positioning or outcome, not independent proof.
- **Design decision / hypothesis:** an AegisAI choice or proposed experiment, not a finding.
Existing source files, [the approved plan](../plan.md), and the separate documentation portal are preserved. Relative links and ordinary Markdown keep this pack suitable for later Docusaurus import. This delivery creates documentation only; no product application, cloud deployment, vendor purchase, or customer communication is represented as completed.